## User Acceptance Testing WBS
USER ACCEPTANCE TESTING WBS TEMPLATE
CLICK HERE TO CREATE IN SMARTSHEET
UAT and Training Completed
Training
Train QA testers
Train agents for service & marketing
Establish customer training hubs
Project-specific roles in place
Allocate supplier test roles (release manager, test-specific author)
Allocate customer roles (QA team, administrators)
Test sites in place
Configuration & customization site in place
Agent test site in place
Training & cstomer test site in place
Testing completed
Prepare for QA
Perform core functionality testing
UAT of customizations
Write test cases from solution design
Book agents' travel & time
Train administrators for service & marketing
Define validation criteria
Write FAQ for testers
Confirm test plan & test schedule

## User Acceptance Testing - BLANK
USER ACCEPTANCE TESTING WBS TEMPLATE

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.