## 90 Day Business Plan Timeline
SAMPLE 90-DAY BUSINESS PLAN TEMPLATE WITH TIMELINE
PLAN TITLE |  | START | END
|  | 2025-07-21 | 2025-10-18
To populate the Month and Day rows, enter the plan's Start and End dates in the columns above. To complete the Timeline Chart, enter each Task in the rows below. |  |  |  | MO. | 07 | 07 | 07 | 07 | 07 | 07 | 07 | 07 | 07 | 07 | 07 | 08 | 08 | 08 | 08 | 08 | 08 | 08 | 08 | 08 | 08 | 08 | 08 | 08 | 08 | 08 | 08 | 08 | 08 | 08 | 08 | 08 | 08 | 08 | 08 | 08 | 08 | 08 | 08 | 08 | 08 | 08 | 09 | 09 | 09 | 09 | 09 | 09 | 09 | 09 | 09 | 09 | 09 | 09 | 09 | 09 | 09 | 09 | 09 | 09 | 09 | 09 | 09 | 09 | 09 | 09 | 09 | 09 | 09 | 09 | 09 | 09 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
|  |  |  | DAY | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
TASKS | OWNER | START | END | DAYS | time axis 2025-07-21 to 2025-10-18
Day 1-30 |  | 2025-07-21 | 2025-08-19 | 30 | bar: 2025-07-21 to 2025-10-18
Phase 1: Description |  | 2025-07-21 | 2025-08-04 | 15 | bar: 2025-07-21 to 2025-10-18
Summarize the business vision |  | 2025-07-22 | 2025-07-23 | 2 | bar: 2025-07-22 to 2025-07-23
Define the problem being solved |  | 2025-07-23 | 2025-07-25 | 3 | bar: 2025-07-23 to 2025-07-25
Research the problem and identify the factors that contribute to it |  | 2025-07-25 | 2025-07-30 | 6 | bar: 2025-07-25 to 2025-07-30
Research your competitors |  | 2025-07-25 | 2025-07-31 | 7 | bar: 2025-07-25 to 2025-07-31
Create Problem/Opportunity Statement |  | 2025-08-01 | 2025-08-04 | 4 | bar: 2025-08-01 to 2025-08-04
Phase 2: Description |  | 2025-08-05 | 2025-08-19 | 15 | bar: 2025-07-21 to 2025-10-18
Research the current solutions to the problem |  | 2025-08-05 | 2025-08-08 | 4 | bar: 2025-08-05 to 2025-08-08
Define who is impacted by the problem and/or who benefits from the solution |  | 2025-08-08 | 2025-08-11 | 4 | bar: 2025-08-08 to 2025-08-11
Identify the gaps and opportunities that make your solution better |  | 2025-08-12 | 2025-08-15 | 4 | bar: 2025-08-12 to 2025-08-15
Conduct formal assessments of the business concept |  | 2025-08-13 | 2025-08-15 | 3 | bar: 2025-08-13 to 2025-08-15
Conduct Interviews with experts and allies |  | 2025-08-13 | 2025-08-16 | 4 | bar: 2025-08-13 to 2025-08-16
Get feedback from the customers of your competitors |  | 2025-08-13 | 2025-08-19 | 7 | bar: 2025-08-13 to 2025-08-19
a. Send surveys |  | 2025-08-13 | 2025-08-13 | 1 | bar: 2025-08-13
b. Customer observation |  | 2025-08-14 | 2025-08-19 | 6 | bar: 2025-08-14 to 2025-08-19
Day 30-60 |  | 2025-08-20 | 2025-09-18 | 30 | bar: 2025-07-21 to 2025-10-18
Phase 3: Description |  | 2025-08-20 | 2025-08-31 | 12 | bar: 2025-07-21 to 2025-10-18
Conduct market research |  | 2025-08-20 | 2025-08-24 | 5 | bar: 2025-08-20 to 2025-08-24
a. Assess the market size |  | 2025-08-20 | 2025-08-22 | 3 | bar: 2025-08-20 to 2025-08-22
b. Assess industry trends |  | 2025-08-21 | 2025-08-23 | 3 | bar: 2025-08-21 to 2025-08-23
c. Analyze the competitive landscape |  | 2025-08-22 | 2025-08-24 | 3 | bar: 2025-08-22 to 2025-08-24
Research your direct competitors |  | 2025-08-24 | 2025-08-26 | 3 | bar: 2025-08-24 to 2025-08-26
Develop a competitive advantage |  | 2025-08-27 | 2025-08-30 | 4 | bar: 2025-08-27 to 2025-08-30
Research industry reports related to your product and industry |  | 2025-08-28 | 2025-08-30 | 3 | bar: 2025-08-28 to 2025-08-30
Determine your marketing mix |  | 2025-08-29 | 2025-08-30 | 2 | bar: 2025-08-29 to 2025-08-30
Evaluate Profitability |  | 2025-08-29 | 2025-08-30 | 2 | bar: 2025-08-29 to 2025-08-30
Review Strategy |  | 2025-08-31 | 2025-08-31 | 1 | bar: 2025-08-31
Phase 4: Description |  | 2025-09-01 | 2025-09-18 | 18 | bar: 2025-07-21 to 2025-10-18
Determine your key business activities |  | 2025-09-01 | 2025-09-04 | 4 | bar: 2025-09-01 to 2025-09-04
Identify your operating costs |  | 2025-09-01 | 2025-09-08 | 8 | bar: 2025-09-01 to 2025-09-08
Identify the resources you need |  | 2025-09-05 | 2025-09-09 | 5 | bar: 2025-09-05 to 2025-09-09
Conduct a SWOT analysis |  | 2025-09-09 | 2025-09-10 | 2 | bar: 2025-09-09 to 2025-09-10
Develop your business model |  | 2025-09-11 | 2025-09-14 | 4 | bar: 2025-09-11 to 2025-09-14
Develop a sustainable unique value proposition |  | 2025-09-14 | 2025-09-15 | 2 | bar: 2025-09-14 to 2025-09-15
Seek strategic partnerships |  | 2025-09-15 | 2025-09-18 | 4 | bar: 2025-09-15 to 2025-09-18
Day 60-90 |  | 2025-09-19 | 2025-10-18 | 30 | bar: 2025-07-21 to 2025-10-18
Phase 5: Description |  | 2025-09-19 | 2025-09-25 | 7 | bar: 2025-07-21 to 2025-10-18
Define your sales targets |  | 2025-09-19 | 2025-09-20 | 2 | bar: 2025-09-19 to 2025-09-20
Outline the steps to achieve your sales goals |  | 2025-09-20 | 2025-09-21 | 2 | bar: 2025-09-20 to 2025-09-21
Develop your sales enablement strategy |  | 2025-09-22 | 2025-09-24 | 3 | bar: 2025-09-22 to 2025-09-24
Create a sales forecast |  | 2025-09-24 | 2025-09-25 | 2 | bar: 2025-09-24 to 2025-09-25
Determine the systems to put in place to support your sales process and goals |  | 2025-09-24 | 2025-09-25 | 2 | bar: 2025-09-24 to 2025-09-25
Phase 6: Description |  | 2025-09-26 | 2025-09-30 | 5 | bar: 2025-07-21 to 2025-10-18
Determine your input costs |  | 2025-09-26 | 2025-09-27 | 2 | bar: 2025-09-26 to 2025-09-27
Establish your selling price |  | 2025-09-27 | 2025-09-28 | 2 | bar: 2025-09-27 to 2025-09-28
Perform a break-even analysis |  | 2025-09-28 | 2025-09-28 | 1 | bar: 2025-09-28
Prepare your startup budget |  | 2025-09-29 | 2025-09-29 | 1 | bar: 2025-09-29
Prepare a pro forma balance sheet |  | 2025-09-30 | 2025-09-30 | 1 | bar: 2025-09-30
Prepare a pro forma income statement |  | 2025-09-30 | 2025-09-30 | 1 | bar: 2025-09-30
Prepare a pro forma cash flow statement |  | 2025-09-30 | 2025-09-30 | 1 | bar: 2025-09-30
Phase 7: Description |  | 2025-10-01 | 2025-10-18 | 18 | bar: 2025-07-21 to 2025-10-18
Document your current and future business goals |  | 2025-10-01 | 2025-10-03 | 3 | bar: 2025-10-01 to 2025-10-03
Develop your mission and vision statement |  | 2025-10-02 | 2025-10-04 | 3 | bar: 2025-10-02 to 2025-10-04
Document your management team |  | 2025-10-04 | 2025-10-04 | 1 | bar: 2025-10-04
Detail your current and future product and service offerings |  | 2025-10-05 | 2025-10-07 | 3 | bar: 2025-10-05 to 2025-10-07
Define the structure of your company |  | 2025-10-08 | 2025-10-09 | 2 | bar: 2025-10-08 to 2025-10-09
Summarize your company's history |  | 2025-10-10 | 2025-10-11 | 2 | bar: 2025-10-10 to 2025-10-11
a. Company timeline and key milestones |  | 2025-10-10 | 2025-10-11 | 2 | bar: 2025-10-10 to 2025-10-11
Formalize your business plan |  | 2025-10-12 | 2025-10-16 | 5 | bar: 2025-10-12 to 2025-10-16
Develop your investor pitch deck |  | 2025-10-16 | 2025-10-18 | 3 | bar: 2025-10-16 to 2025-10-18
CLICK HERE TO CREATE IN SMARTSHEET | bar: 2025-07-21 to 2025-08-19

## 90 Day Business Plan - BLANK
SAMPLE 90 DAY BUSINESS PLAN TEMPLATE WITH TIMELINE
PLAN TITLE |  | START | END
|  | 2025-07-21 | 2025-10-18
Enter Start and End dates above for the plan to populate the Month and Day rows, and below for each Task to complete the Timeline Chart. |  |  |  | MO. | 07 | 07 | 07 | 07 | 07 | 07 | 07 | 07 | 07 | 07 | 07 | 08 | 08 | 08 | 08 | 08 | 08 | 08 | 08 | 08 | 08 | 08 | 08 | 08 | 08 | 08 | 08 | 08 | 08 | 08 | 08 | 08 | 08 | 08 | 08 | 08 | 08 | 08 | 08 | 08 | 08 | 08 | 09 | 09 | 09 | 09 | 09 | 09 | 09 | 09 | 09 | 09 | 09 | 09 | 09 | 09 | 09 | 09 | 09 | 09 | 09 | 09 | 09 | 09 | 09 | 09 | 09 | 09 | 09 | 09 | 09 | 09 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
|  |  |  | DAY | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
TASKS | OWNER | START | END | DAYS | time axis 2025-07-21 to 2025-10-18
Day 1-30 |  |  |  | 1
Phase 1: Description |  |  |  | 1
Summarize business vision |  |  |  | 1
Define problem being solved |  |  |  | 1
Research the problem and identify factors that contribute to it |  |  |  | 1
Research competitors |  |  |  | 1
Create Problem / Opportunity Statement |  |  |  | 1
Phase 2: Description |  |  |  | 1
Research current solutions to the problem |  |  |  | 1
Define who is impacted by the problem and/or who benefits from the solution |  |  |  | 1
Identify gaps and opportunities that make your solution better |  |  |  | 1
Conduct formal assessments of business concept |  |  |  | 1
Conduct Interviews with experts and allies |  |  |  | 1
Get feedback from customers of competitors |  |  |  | 1
a. Send surveys |  |  |  | 1
b. Customer observation |  |  |  | 1
Day 30-60 |  |  |  | 1
Phase 3: Description |  |  |  | 1
Conduct market research |  |  |  | 1
a. Assess market size |  |  |  | 1
b. Assess industry trends |  |  |  | 1
c. Analyze competitive landscape |  |  |  | 1
Research direct competitors |  |  |  | 1
Develop competitive advantage |  |  |  | 1
Research industry reports related to your product and industry |  |  |  | 1
Determine marketing mix |  |  |  | 1
Evaluate Profitability |  |  |  | 1
Review Strategy |  |  |  | 1
Phase 4: Description |  |  |  | 1
Determine key business activities |  |  |  | 1
Identify operating costs |  |  |  | 1
Identify resources needed |  |  |  | 1
Conduct SWOT Analysis |  |  |  | 1
Develop business model |  |  |  | 1
Develop sustainable unique value proposition |  |  |  | 1
Seek strategic partnerships |  |  |  | 1
Day 60-90 |  |  |  | 1
Phase 5: Description |  |  |  | 1
Define sales targets |  |  |  | 1
Outline steps to achieve sales goals |  |  |  | 1
Develop sales enablement strategy |  |  |  | 1
Create sales forecast |  |  |  | 1
Determine systems to put in place to support sales process and goals |  |  |  | 1
Phase 6: Description |  |  |  | 1
Determine input costs |  |  |  | 1
Establish selling price |  |  |  | 1
Perform break-even analysis |  |  |  | 1
Prepare startup budget |  |  |  | 1
Prepare pro forma balance sheet |  |  |  | 1
Prepare pro forma income statement |  |  |  | 1
Prepare for forma cash flow statement |  |  |  | 1
Phase 7: Description |  |  |  | 1
Document current and future business goals |  |  |  | 1
Develop mission and vision statement |  |  |  | 1
Document management team |  |  |  | 1
Detail current and future product and service offerings |  |  |  | 1
Define structure of company |  |  |  | 1
Summarize company history |  |  |  | 1
a. Company timeline and key milestones |  |  |  | 1
Formalize business plan |  |  |  | 1
Develop investor pitch deck |  |  |  | 1

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.