## Sheet1
ACTION PLAN TEMPLATE
Project Name | Event ABC
Project Manager | Anthony G.
Action | Responsible | Priority | Status | Start Date | End Date | Notes
Goal #1: Select Venue
Identify venue options | Sally J. | High | Complete | 2015-09-30 | 2015-10-02
Visit venues | Sally J. | High | Complete | 2015-10-05 | 2015-10-09 | Must send contracts by 10/10
Sign contract | Maria S. | High | Complete | 2015-10-12 | 2015-10-12
Goal #2: Secure Speakers
Recruit speakers | Sally J. | High | In progress | 2015-10-07 | 2015-10-12
Speaker bios | Sally J. | Medium | Not started | 2015-10-12 | 2015-10-14
Create and send speaker packets | Maria S. | Medium | Not started | 2015-10-13 | 2015-10-16 | Send to stakeholders
Confirm speakers | Sally J. | High | Not started | 2015-10-17 | 2015-10-18
Goal #3: Recruit Sponsors
Identify sponsors | John S. | High | In progress | 1902-10-13 | 2015-10-19
Write up sponsor agreement | Maria S. | Medium | Not started | 2015-10-15 | 2015-10-16
Send emails | John S. | High | In progress | 2015-10-19 | 2015-10-21
Make cold calls | John S. | Medium | Not started | 2015-10-21 | 2015-10-23 | From sales team
Goal #4: Promote event
Create banners | Morgan K. | Low | Not started | 2015-10-26 | 2015-10-28
Order swag | Morgan K. | Low | Not started | 2015-10-28 | 2015-10-28 | Coffee mugs, totes, pencils
Create social media strategy | Corrine J. | Low | In progress | 2015-10-13 | 2015-10-26
Make marketing materials | Karen Z. | High | Not started | 2015-10-26 | 2015-10-30
CREATE YOUR ACTION PLAN IN SMARTSHEET

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.