## Mktg Project Mgmt Dashboard
MARKETING PROJECT MANAGEMENT DASHBOARD TEMPLATE
CAMPAIGN NAME |  |  |  | DATE | PROJECT STATUS | % COMPLETE
|  |  |  | 00/00/00 | ON TRACK | 72%
TASK TIMELINE
DASHBOARD DATA
TASK TABLE
TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION in days | STATUS | PRIORITY | COMMENTS | STATUS | PRIORITY
Set Kick-Off Meeting |  | 2024-01-02 | 2024-01-08 | 6 | Complete | High |  | Not Started | High
Agree on Objectives |  | 2024-01-04 | 2024-01-11 | 7 | Complete | Medium |  | In Progress | Medium
Determine Staffing |  | 2024-01-07 | 2024-01-11 | 4 | Complete | Low |  | Complete | Low
Develop Messaging |  | 2024-01-10 | 2024-01-15 | 5 | Complete | Low |  | Overdue
Finalize Budget |  | 2024-01-13 | 2024-01-20 | 7 | Complete | Low |  | On Hold
Email Outreach |  | 2024-01-16 | 2024-01-29 | 13 | Overdue | High
Design Landing Page |  | 2024-01-19 | 2024-02-01 | 13 | In Progress | High
Targeted Blog Post |  | 2024-01-22 | 2024-02-09 | 18 | In Progress | High
Video Production |  | 2024-01-25 | 2024-02-05 | 11 | In Progress | High
Ad Content |  | 2024-01-28 | 2024-02-06 | 9 | On Hold | High
Social Media Promotion |  | 2024-01-31 | 2024-02-02 | 2 | Not Started | Medium
TASK STATUS % |  |  |  | BUDGET
STATUS | COUNT | % |  | PLANNED | 80000
Not Started | 1 | 9.091% |  | ACTUAL | 50000
In Progress | 3 | 27.27%
Complete | 5 | 45.45%
Overdue | 1 | 9.091%
On Hold | 1 | 9.091%
TOTAL | 11 | 100%
TASK PRIORITY % |  |  |  | PENDING ITEMS
PRIORITY | COUNT | % |  | Decisions | 5
High | 6 | 54.55% |  | Actions | 2
Medium | 2 | 18.18% |  | Change Requests | 4
Low | 3 | 27.27%
| 0 | 0%
TOTAL | 11 | 100%
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Mktg Project Mgmt Dash
MARKETING PROJECT MANAGEMENT DASHBOARD
CAMPAIGN NAME |  |  |  | DATE | PROJECT STATUS | % COMPLETE
|  |  |  | 00/00/00 | ON TRACK | 100% | Enter DASHBOARD DATA in the tables beginning at row 8. Dashboard graphics will automatically populate.
TASK TIMELINE
DASHBOARD DATA
TASK TABLE
TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION in days | STATUS | PRIORITY | COMMENTS | STATUS | PRIORITY
Set Kick-Off Meeting |  |  |  | 0 |  |  |  | Not Started | High
Agree on Objectives |  |  |  | 0 |  |  |  | In Progress | Medium
Determine Staffing |  |  |  | 0 |  |  |  | Complete | Low
Develop Messaging |  |  |  | 0 |  |  |  | Overdue
Finalize Budget |  |  |  | 0 |  |  |  | On Hold
Email Outreach |  |  |  | 0
Design Landing Page |  |  |  | 0
Targeted Blog Post |  |  |  | 0
Video Production |  |  |  | 0
Ad Content |  |  |  | 0
Social Media Promotion |  |  |  | 0
Task 12 |  |  |  | 0
Task 13 |  |  |  | 0
Task 14 |  |  |  | 0
Task 15 |  |  |  | 0
Task 16 |  |  |  | 0
Task 17 |  |  |  | 0
Task 18 |  |  |  | 0
Task 19 |  |  |  | 0
Task 20 |  |  |  | 0
TASK STATUS % | automatically populates |  |  | BUDGET
STATUS | COUNT | % |  | PLANNED | 0
Not Started | 0 |  |  | ACTUAL | 0
In Progress | 0
Complete | 0
Overdue | 0
On Hold | 0
TOTAL | 0 | 0%
TASK PRIORITY % | automatically populates |  |  | PENDING ITEMS
PRIORITY | COUNT | % |  | Decisions | 0
High | 0 |  |  | Actions | 0
Medium | 0 |  |  | Change Requests | 0
Low | 0
0
TOTAL | 0 | 0%
Right-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.