## Project Pipeline Tracker
PROJECT PIPELINE TRACKER TEMPLATE
CAMPAIGN NAME |  |  |  | DATE | STATUS | # COMPLETE | % COMPLETE | # AT RISK | AVG DAYS TO COMPLETE
|  |  |  | 00/00/00 | ON TRACK | 3 | 27.27% | 1 | 78
DASHBOARD DATA
PROJECTS
PROJECT ID | NAME | START DATE | RESEARCH END DATE | APPROVAL END DATE | DEVELOP END DATE | TEST END DATE | EXECUTE END DATE | LAUNCH END DATE | DURATION in days | STAGE | STATUS | TYPE | COMMENTS | STAGE | STATUS | TYPE
1 | alpha | 2027-01-02 | 2027-01-08 | 2027-01-15 | 2027-01-27 | 2027-01-31 | 2027-02-20 | 2027-02-28 | 57 | Launch | Complete | Hybrid |  | Research | Not Started | Internal
2 | beta | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-02-04 | 2027-02-18 |  |  | 0 | Test | In Progress | External |  | Approval | In Progress | External
3 | gamma | 2027-01-02: 2027-01-07; 2027-01-08: 2027-01-11; 2027-01-15: 2027-01-28; 2027-01-27: 2027-01-31 | 0 | Develop | In Progress | External |  | Develop | Complete | Hybrid
4 | delta | 2027-01-02: 2027-01-10; 2027-01-08: 2027-01-15; 2027-01-15: 2027-02-22 | 0 | Approval | In Progress | Internal |  | Test | Overdue
5 | epsilon | 2027-01-02: 2027-01-13; 2027-01-08: 2027-01-20 | 0 | Research | Not Started | Internal |  | Execute | On Hold
6 | zêta | 2027-01-02: 2027-01-16; 2027-01-08: 2027-01-29; 2027-01-15: 2027-02-14 | 0 | Approval | Overdue | Internal |  | Launch | At Risk
7 | êta | 2027-01-02: 2027-01-19; 2027-01-08: 2027-02-01; 2027-01-15: 2027-02-11; 2027-01-27: 2027-02-21 | 0 | Develop | On Hold | External
8 | thêta | 2027-01-22 | 2027-02-09 | 2027-02-19 | 2027-02-25 | 2027-03-09 |  |  | 0 | Test | At Risk | Internal
9 | iota | 2027-01-25 | 2027-02-05 | 2027-02-15 | 2027-02-25 | 2027-02-28 | 2027-03-14 |  | 0 | Execute | In Progress | Hybrid
10 | kappa | 2027-01-28 | 2027-02-06 | 2027-03-02 | 2027-03-26 | 2027-04-06 | 2027-04-16 | 2027-04-20 | 82 | Launch | Complete | External
11 | lambda | 2027-01-31 | 2027-02-02 | 2027-03-02 | 2027-03-05 | 2027-04-02 | 2027-04-22 | 2027-05-06 | 95 | Launch | Complete | Internal
|  | 2027-01-31: PROJECT STAGE %; 2027-04-02: PROJECT STATUS % |  | TASK TYPE %
|  | STAGE | COUNT | % |  | STATUS | COUNT | % |  | STATUS | COUNT | %
|  | Research | 1 | 9.091% |  | Not Started | 1 | 10% |  | INTERNAL | 5 | 45.45%
|  | Approval | 2 | 18.18% |  | In Progress | 4 | 40% |  | EXTERNAL | 4 | 36.36%
|  | Develop | 2 | 18.18% |  | Complete | 3 | 30% |  | HYBRID | 2 | 18.18%
|  | Test | 2 | 18.18% |  | Overdue | 1 | 10% |  | TOTAL | 11 | 100%
|  | Execute | 1 | 9.091% |  | On Hold | 1 | 10%
|  | Launch | 3 | 27.27% |  | At Risk | 1 | 10%
|  | TOTAL | 11 | 100% |  | TOTAL | 10 | 100%
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK- Project Pipeline Tracker
PROJECT PIPELINE TRACKER TEMPLATE
CAMPAIGN NAME |  |  |  | DATE | STATUS | # COMPLETE | % COMPLETE | # AT RISK | AVG DAYS TO COMPLETE
|  |  |  | 00/00/00 | ON TRACK | 0 | 0 | 0
DASHBOARD DATA
PROJECTS
PROJECT ID | NAME | START DATE | RESEARCH END DATE | APPROVAL END DATE | DEVELOP END DATE | TEST END DATE | EXECUTE END DATE | LAUNCH END DATE | DURATION in days | STAGE | STATUS | TYPE | COMMENTS | STAGE | STATUS | TYPE
[9 empty] | 0 |  |  |  |  | Research | Not Started | Internal
[9 empty] | 0 |  |  |  |  | Approval | In Progress | External
[9 empty] | 0 |  |  |  |  | Develop | Complete | Hybrid
[9 empty] | 0 |  |  |  |  | Test | Overdue
[9 empty] | 0 |  |  |  |  | Execute | On Hold
[9 empty] | 0 |  |  |  |  | Launch | At Risk
0
0
0
0
0
|  | PROJECT STAGE % |  |  |  | PROJECT STATUS % |  |  |  | TASK TYPE %
|  | STAGE | COUNT | % |  | STATUS | COUNT | % |  | STATUS | COUNT | %
|  | Research | 0 |  |  | Not Started | 0 |  |  | INTERNAL | 0
|  | Approval | 0 |  |  | In Progress | 0 |  |  | EXTERNAL | 0
|  | Develop | 0 |  |  | Complete | 0 |  |  | HYBRID | 0
|  | Test | 0 |  |  | Overdue | 0 |  |  | TOTAL | 0 | 0%
|  | Execute | 0 |  |  | On Hold | 0
|  | Launch | 0 |  |  | At Risk | 0
|  | TOTAL | 0 | 0% |  | TOTAL | 0 | 0%
Enter DASHBOARD DATA in the tables beginning at row 10.
Dashboard graphics will automatically populate.
User to complete non-shaded cells only.

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.