## Subcontractor Doc Tracker
SUBCONTRACTOR DOCUMENTATION TRACKER
PROJECT NAME | [5 empty] | PROJECT DESCRIPTION
PRIMARY CONTRACTOR
PROJECT MANAGER
SUB ID | PHASE | SUBCONTRACTOR COMPANY NAME | CONTACT NAME | CONTACT PHONE | CONTACT EMAIL | SCOPE OF WORK | DURATION OF WORK | CONTRACT AMOUNT | INSURANCE RECEIVED | CONTRACT EXECUTED | NOTICE TO PROCEED ISSUED | LICENSE VERIFIED | SCHEDULE OF WORK RECEIVED | SHOP DRAWINGS PROVIDED | PUNCHLIST COMPLETE | OTHER REQUIRED DOCUMENTATION (i.e.. Request to Sublet, Statement of Intent, etc.) | PHASE KEY
1 | Electrical | Subcontractor A | Jim | 818-555-5198 | jim@subcontractora.com | Provide & install all electrical conduits to ensure interior lights work according to plans and specification | 15 working days | 15000 | 2026-10-15 | 2026-10-15 | 2026-10-16 | ü | ü | ü | ü |  | Electrical
| Mechanical | [10 empty] | ü | ü | ü | ü |  | Mechanical
| Plumbing | [10 empty] | ü | ü | ü | ü |  | Plumbing
| Utilities | [10 empty] | ü | ü | ü | ü |  | Utilities
| Framework | [10 empty] | ü | ü | ü | ü |  | Framework
| Concrete | [10 empty] | ü | ü | ü | ü |  | Concrete
| Landscape | [10 empty] | ü | ü | ü | ü |  | Landscape
| HVAC | [10 empty] | ü | ü | ü | ü |  | HVAC
| Other | [10 empty] | ü | ü | ü | ü |  | Other
[12 empty] | ü | ü | ü | ü |  | Other
[12 empty] | ü | ü | ü | ü |  | Other
[12 empty] | ü | ü | ü | ü |  | Other
[12 empty] | ü | ü | ü | ü |  | Other
[12 empty] | ü | ü | ü | ü |  | Other
CLICK HERE TO CREATE IN SMARTSHEET

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.