## Application for Payment
BUILDING CONSTRUCTION INVOICE SAMPLE TEMPLATE
Blank Application for Payment can be found on the next tab.
APPLICATION FOR PAYMENT
[10 empty] | APPLICATION NUMBER | 2
| TO OWNER | [5 empty] | PROJECT
| SMITH BUILDING | [5 empty] | TENANT IMPROVEMENTS PHASE 1 |  |  | PERIOD ENDING | 11/11/20XX
[10 empty] | CONTRACT WORK | CABINETRY
FROM CONTRACTOR
| ELITE CONSTRUCTION | [8 empty] | CONTRACT NO | 102015
[10 empty] | PREPARED BY | M. McCLELLAN
CONTRACTOR'S APPLICATION FOR PAYMENT | [7 empty] | CONTRACTOR'S CERTIFICATION
Refer to backup sheets attached for detailed breakdown | [7 empty] | The undersigned Contractor to the best of his knowledge, information and believe of the Work covered by this Application for Payment has been completed in accordance with the Contract Documents, that all amounts have been paid to him for Work for which previous Certificates for Payment were issues and payments received from the Owner, and that current payment shown herein is now due.
1 | Original Contract Amount: |  |  |  | 48500
2 | Net Changes to Contract: |  |  |  | 950 |  |  | CONTRACTOR |  |  | DATE
3 | Total Contract Amount: |  |  |  | 49450
4 | Total Completed To Date: |  |  |  | 36000 |  |  | State |  | Country
5 | Retainage: | [6 empty] | Subscribed & sworn to before me
| a. | 15% | of Completed Work |  |  |  |  | this | day of
| Total Retainage: |  |  |  | 5400
[8 empty] | Notary Public Name |  |  | Commission Expiration Date
6 | Total Completed Less Retainage: |  |  |  | 30600
7 | Less Previous Applications: |  |  |  | 10000 |  |  | ENGINEER'S CERTIFICATE FOR PAYMENT
The Engineer hereby confirms that based on site observations & to the best of his/her knowledge, this payment application accurately reflects the progression of work and that this work meets contract requirements sufficient enough to justify payment in the amount certified below:
8 | Current Payment Due: |  |  |  | 20600
9 | Balance to Finish Including Retainage: |  |  |  | 18850 |  |  | AMOUNT CERTIFIED
Provide explanation below or attached if amount certified does not match this application amount. Initial all figures & markups to agree with certified amount.
EXTRA WORK SUMMARY |  |  |  | ADDITIONS |  | DELETIONS
Changes From Previous Applications |  |  |  |  | 2750 |  | 1800 | ENGINEER |  |  | DATE
Changes From This Application |  |  |  |  | 0 |  | 0
Total |  |  |  |  | 2750 |  | 1800 | The Amount Certified is payable to the contractor listed above.
Net Changes |  |  |  |  | 950
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Application for Payment
CONTRACTOR PROGRESS PAYMENT TEMPLATE
APPLICATION FOR PAYMENT
APPLICATION NUMBER
| TO OWNER | [5 empty] | PROJECT
PERIOD ENDING
CONTRACT WORK
FROM CONTRACTOR
CONTRACT NO
PREPARED BY
CONTRACTOR'S APPLICATION FOR PAYMENT | [7 empty] | CONTRACTOR'S CERTIFICATION
Refer to backup sheets attached for detailed breakdown | [7 empty] | The undersigned Contractor to the best of his knowledge, information and believe of the Work covered by this Application for Payment has been completed in accordance with the Contract Documents, that all amounts have been paid to him for Work for which previous Certificates for Payment were issues and payments received from the Owner, and that current payment shown herein is now due.
1 | Original Contract Amount: |  |  |  | 0
2 | Net Changes to Contract: |  |  |  | 0 |  |  | CONTRACTOR |  |  | DATE
3 | Total Contract Amount: |  |  |  | 0
4 | Total Completed To Date: |  |  |  | 0 |  |  | State |  | Country
5 | Retainage: | [6 empty] | Subscribed & sworn to before me
| a. | 0% | of Completed Work |  |  |  |  | this | day of
| Total Retainage: |  |  |  | 0
[8 empty] | Notary Public Name |  |  | Commission Expiration Date
6 | Total Completed Less Retainage: |  |  |  | 0
7 | Less Previous Applications: |  |  |  | 0 |  |  | ENGINEER'S CERTIFICATE FOR PAYMENT
The Engineer hereby confirms that based on site observations & to the best of his/her knowledge, this payment application accurately reflects the progression of work and that this work meets contract requirements sufficient enough to justify payment in the amount certified below:
8 | Current Payment Due: |  |  |  | 0
9 | Balance to Finish Including Retainage: |  |  |  | 0 |  |  | AMOUNT CERTIFIED
Provide explanation below or attached if amount certified does not match this application amount. Initial all figures & markups to agree with certified amount.
EXTRA WORK SUMMARY |  |  |  | ADDITIONS |  | DELETIONS
Changes From Previous Applications |  |  |  |  | 0 |  | 0 | ENGINEER |  |  | DATE
Changes From This Application |  |  |  |  | 0 |  | 0
Total |  |  |  |  | 0 |  | 0 | The Amount Certified is payable to the contractor listed above.
Net Changes |  |  |  |  | 0

## Progress Payment Backup
PROGRESS PAYMENT BACKUP
BID ITEM # | TASK DESCRIPTION | CONTRACTOR OR SUBCONTRACTOR | CONTRACT SUM | WORK COMPLETE (%) | AMOUNT VALUED | CONTRACTOR'S CLAIM | AMOUNT PAYABLE | REASON FOR DIFFERENCE
EXCAVATION & EARTHWORK
1.001 | Cut & Fill |  |  |  | 0 |  | 0 | n/a
1.002 | Removal of Stone/Dirt |  |  |  | 0 |  | 0 | n/a
1.003 | Trenching For Utility Hookups |  |  |  | 0 |  | 0 | n/a
1.004 | Foundation Excavation |  |  |  | 0 |  | 0 | n/a
1.005 | Foundation Footing Drains |  |  |  | 0 |  | 0 | n/a
1.006 | Curtain Drains |  |  |  | 0 |  | 0 | n/a
1.007 | Culverts |  |  |  | 0 |  | 0 | n/a
1.008 | Swales |  |  |  | 0 |  | 0 | n/a
1.009 | Retaining Walls |  |  |  | 0 |  | 0 | n/a
1.01 | Ponds |  |  |  | 0 |  | 0 | n/a
1.011 | Other Site Drainage |  |  |  | 0 |  | 0 | n/a
1.012 | Backfill |  |  |  | 0 |  | 0 | n/a
1.013 | Compaction |  |  |  | 0 |  | 0 | n/a
1.014 | Top Soil |  |  |  | 0 |  | 0 | n/a
1.015 | Finish Grading |  |  |  | 0 |  | 0 | n/a
1.016 | Seeding/Sod |  |  |  | 0 |  | 0 | n/a
0
FOUNDATION
2.001 | Footings/Pads |  |  |  | 0 |  | 0 | n/a
2.002 | Foundation walls/stem walls/grade beams |  |  |  | 0 |  | 0 | n/a
2.003 | Piers |  |  |  | 0 |  | 0 | n/a
2.004 | Slabs - Foundation, Basement, Garage |  |  |  | 0 |  | 0 | n/a
2.005 | Steel Reinforcing |  |  |  | 0 |  | 0 | n/a
2.006 | Anchor Bolts, Hold Downs |  |  |  | 0 |  | 0 | n/a
2.007 | Bulkheads |  |  |  | 0 |  | 0 | n/a
2.008 | Sub-Slab Vapor Barrier |  |  |  | 0 |  | 0 | n/a
2.009 | Sump Pump |  |  |  | 0 |  | 0 | n/a
2.01 | Crawlspace Vapor Barrier |  |  |  | 0 |  | 0 | n/a
2.011 | Crawlspace Vents |  |  |  | 0 |  | 0 | n/a
2.012 | Foundation Windows |  |  |  | 0 |  | 0 | n/a
2.013 | Dam-proofing, Water-proofing |  |  |  | 0 |  | 0 | n/a
2.014 | Foundation Drain Board |  |  |  | 0 |  | 0 | n/a
2.015 | Slab insulation: Edge/Blow |  |  |  | 0 |  | 0 | n/a
2.016 | Exterior Foundation Insulation |  |  |  | 0 |  | 0 | n/a
2.017 | Exterior Insulation Coating/ Protection |  |  |  | 0 |  | 0 | n/a
0
OTHER MASONRY/PAVING
3.001 | Patios |  |  |  | 0 |  | 0 | n/a
3.002 | Exterior Stairs |  |  |  | 0 |  | 0 | n/a
3.003 | Masonry Chimneys |  |  |  | 0 |  | 0 | n/a
3.004 | Fireplaces/Hearths |  |  |  | 0 |  | 0 | n/a
3.005 | Driveway |  |  |  | 0 |  | 0 | n/a
3.006 | Walkways |  |  |  | 0 |  | 0 | n/a
0
ROUGH FRAMING
4.001 | Sill & Seal |  |  |  | 0 |  | 0 | n/a
4.002 | Steel/Wood Carrying Beam, Lolly Columns |  |  |  | 0 |  | 0 | n/a
4.003 | Floor Framing |  |  |  | 0 |  | 0 | n/a
4.004 | Exterior & Interior Walls, Rough Stairs |  |  |  | 0 |  | 0 | n/a
4.005 | Sheathing, Subflooring |  |  |  | 0 |  | 0 | n/a
4.006 | Roof Framing/Trusses |  |  |  | 0 |  | 0 | n/a
4.007 | Sub fascia |  |  |  | 0 |  | 0 | n/a
4.008 | Steel Framing Connectors |  |  |  | 0 |  | 0 | n/a
4.009 | Nails, Screws, Fasteners |  |  |  | 0 |  | 0 | n/a
4.01 | Prep for Plaster, Drywall |  |  |  | 0 |  | 0 | n/a
4.011 | Rough Framing - Labor Only |  |  |  | 0 |  | 0 | n/a
0
EXTERIOR
5.001 | Exterior Foam Sheathing |  |  |  | 0 |  | 0 | n/a
5.002 | Weather Barrier (Tyvek, etc.) |  |  |  | 0 |  | 0 | n/a
5.003 | Membrance & Flashing |  |  |  | 0 |  | 0 | n/a
5.004 | Vinyl or Composite Siding |  |  |  | 0 |  | 0 | n/a
5.005 | Wood Siding |  |  |  | 0 |  | 0 | n/a
5.006 | Brick Veneer |  |  |  | 0 |  | 0 | n/a
5.007 | Stone Veneer |  |  |  | 0 |  | 0 | n/a
5.008 | Stucco |  |  |  | 0 |  | 0 | n/a
5.009 | Fascia, Frieze, Corner Boards, Water Table |  |  |  | 0 |  | 0 | n/a
5.01 | Soffit/Gable Vents |  |  |  | 0 |  | 0 | n/a
5.011 | Window/Door Trim |  |  |  | 0 |  | 0 | n/a
5.012 | Other Exterior Trim |  |  |  | 0 |  | 0 | n/a
5.013 | Exterior Paint, Stain, Caulk |  |  |  | 0 |  | 0 | n/a
5.014 | Exterior, labor-only |  |  |  | 0 |  | 0 | n/a
0
WINDOWS/EXTERIOR DOORS
6.001 | Membrane & Flashing |  |  |  | 0 |  | 0 | n/a
6.002 | Exterior doors, prehung |  |  |  | 0 |  | 0 | n/a
6.003 | Exterior door slabs |  |  |  | 0 |  | 0 | n/a
6.004 | Exterior door frames, sills |  |  |  | 0 |  | 0 | n/a
6.005 | Sidelights, transoms |  |  |  | 0 |  | 0 | n/a
6.006 | Locksets, knobs, door hardware |  |  |  | 0 |  | 0 | n/a
6.007 | Patio doors: sliding or hinged |  |  |  | 0 |  | 0 | n/a
6.008 | Windows |  |  |  | 0 |  | 0 | n/a
6.009 | Garage Doors & Opener |  |  |  | 0 |  | 0 | n/a
0
PLUMBING
7.001 | Drain/Waste/Vent |  |  |  | 0 |  | 0 | n/a
7.002 | Water Supply Piping |  |  |  | 0 |  | 0 | n/a
7.003 | Gas Piping |  |  |  | 0 |  | 0 | n/a
7.004 | Water Treatment |  |  |  | 0 |  | 0 | n/a
7.005 | Water Heater |  |  |  | 0 |  | 0 | n/a
7.006 | Fixtures: Toilets, Tubs, Sinks, Showers |  |  |  | 0 |  | 0 | n/a
7.007 | Faucets, Mixing Valves, Shower Heads |  |  |  | 0 |  | 0 | n/a
7.008 | Disposal |  |  |  | 0 |  | 0 | n/a
0
ELECTRICAL
8.001 | Service, Panel, Sub-Panels |  |  |  | 0 |  | 0 | n/a
8.002 | Rough Wiring |  |  |  | 0 |  | 0 | n/a
8.003 | Phone, Cable, Internet Wiring |  |  |  | 0 |  | 0 | n/a
8.004 | Lighting Fixtures |  |  |  | 0 |  | 0 | n/a
8.005 | Low-Voltage Fixtures/Transformers |  |  |  | 0 |  | 0 | n/a
8.006 | Exterior Lighting |  |  |  | 0 |  | 0 | n/a
8.007 | Devices: outlets, switches, dimmers |  |  |  | 0 |  | 0 | n/a
8.008 | Lighting control system |  |  |  | 0 |  | 0 | n/a
8.009 | Doorbell System |  |  |  | 0 |  | 0 | n/a
8.01 | Smoke, CO2 Alarms |  |  |  | 0 |  | 0 | n/a
8.011 | Intercom system |  |  |  | 0 |  | 0 | n/a
8.012 | Security system |  |  |  | 0 |  | 0 | n/a
8.013 | Home theater/Entertainment |  |  |  | 0 |  | 0 | n/a
0
HVAC
9.001 | Furnace/Heat Pump |  |  |  | 0 |  | 0 | n/a
9.002 | Central AC |  |  |  | 0 |  | 0 | n/a
9.003 | Air Handler |  |  |  | 0 |  | 0 | n/a
9.004 | Ductwork, Grilles, Registers |  |  |  | 0 |  | 0 | n/a
9.005 | Air Filter |  |  |  | 0 |  | 0 | n/a
9.006 | Boiler, Piping |  |  |  | 0 |  | 0 | n/a
9.007 | Radiators |  |  |  | 0 |  | 0 | n/a
9.008 | Whole-House Ventilation (HRV, ERV, Exhaust Only, Other) |  |  |  | 0 |  | 0 | n/a
9.009 | HVAC Controls |  |  |  | 0 |  | 0 | n/a
9.01 | Solar hot water |  |  |  | 0 |  | 0 | n/a
0
INSULATION & AIR-SEALING
10.001 | Roof/Attic Insulation |  |  |  | 0 |  | 0 | n/a
10.002 | Roof/Eave Baffles |  |  |  | 0 |  | 0 | n/a
10.003 | Wall Cavity Insulation |  |  |  | 0 |  | 0 | n/a
10.004 | Foam Board Insulation |  |  |  | 0 |  | 0 | n/a
10.005 | Spray Foam Insulation |  |  |  | 0 |  | 0 | n/a
10.006 | Basement Insulation |  |  |  | 0 |  | 0 | n/a
10.007 | Crawlspace Insulation |  |  |  | 0 |  | 0 | n/a
10.008 | Air Sealing |  |  |  | 0 |  | 0 | n/a
10.009 | Energy Diagnostics (Blower Door, Infrared) |  |  |  | 0 |  | 0 | n/a
0
DRYWALL/PLASTER
11.001 | Walls |  |  |  | 0 |  | 0 | n/a
11.002 | Ceilings, Soffits |  |  |  | 0 |  | 0 | n/a
11.003 | Decorative Plaster |  |  |  | 0 |  | 0 | n/a
11.004 | Drywall Labor Only |  |  |  | 0 |  | 0 | n/a
0
INTERIOR FINISH
12.001 | Interior Doors, prehung |  |  |  | 0 |  | 0 | n/a
12.002 | Interior Door slabs |  |  |  | 0 |  | 0 | n/a
12.003 | Interior Door frames, thresholds |  |  |  | 0 |  | 0 | n/a
12.004 | Door knobs, hardware |  |  |  | 0 |  | 0 | n/a
12.005 | Chair Rail, Other |  |  |  | 0 |  | 0 | n/a
12.006 | Wainscotting, Paneling |  |  |  | 0 |  | 0 | n/a
12.007 | Built-in Shelving, Cabinets |  |  |  | 0 |  | 0 | n/a
12.008 | Closet Shelving, Hardware |  |  |  | 0 |  | 0 | n/a
12.009 | Stairs, Railings, Newels |  |  |  | 0 |  | 0 | n/a
12.01 | Interior Painting, Staining |  |  |  | 0 |  | 0 | n/a
12.011 | Wood Flooring |  |  |  | 0 |  | 0 | n/a
12.012 | Carpeting |  |  |  | 0 |  | 0 | n/a
12.013 | Resilient/Vinyl Flooring |  |  |  | 0 |  | 0 | n/a
12.014 | Other Flooring |  |  |  | 0 |  | 0 | n/a
12.015 | Acoustical, Metal, Decorative Ceilings |  |  |  | 0 |  | 0 | n/a
12.016 | Interior Carpentry Labor Only |  |  |  | 0 |  | 0 | n/a
0
KITCHEN & BATH
13.001 | Kitchen Cabinets |  |  |  | 0 |  | 0 | n/a
13.002 | Bath Cabinets |  |  |  | 0 |  | 0 | n/a
13.003 | Cabinet Pulls, Hardware |  |  |  | 0 |  | 0 | n/a
13.004 | Countertop, Backsplash |  |  |  | 0 |  | 0 | n/a
13.005 | Ceramic Tile, Stone |  |  |  | 0 |  | 0 | n/a
13.006 | Raised Tub Platform |  |  |  | 0 |  | 0 | n/a
13.007 | Tub Enclosure |  |  |  | 0 |  | 0 | n/a
13.008 | Shower enclosure/doors |  |  |  | 0 |  | 0 | n/a
13.009 | Medicine Cabinets |  |  |  | 0 |  | 0 | n/a
13.01 | Mirrors |  |  |  | 0 |  | 0 | n/a
13.011 | Towel hangers, toilet paper holders, accessories |  |  |  | 0 |  | 0 | n/a
13.012 | K&B Labor Only |  |  |  | 0 |  | 0 | n/a
0
PORCHES & DECKS
14.001 | Open Porch |  |  |  | 0 |  | 0 | n/a
14.002 | Screen Porch |  |  |  | 0 |  | 0 | n/a
14.003 | Wood or Composite Deck |  |  |  | 0 |  | 0 | n/a
14.004 | Fencing |  |  |  | 0 |  | 0 | n/a
0
APPLIANCES
15.001 | Refrigerator |  |  |  | 0 |  | 0 | n/a
15.002 | Range, Cooktop |  |  |  | 0 |  | 0 | n/a
15.003 | Microwave |  |  |  | 0 |  | 0 | n/a
15.004 | Range Hood |  |  |  | 0 |  | 0 | n/a
15.005 | Dishwasher |  |  |  | 0 |  | 0 | n/a
15.006 | Washer/Dryer |  |  |  | 0 |  | 0 | n/a
0
TOTAL | [6 empty] | 0

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.