## Multi-Project Gantt Chart
MULTI-PROJECT GANTT CHART PLANNER
COMPANY NAME |  |  |  |  | START DATE
2025-03-31
|  | PROJECTS | [5 empty] | DELIVERABLES |  | COST / HOURS |  |  | Wk 1 |  |  |  |  | Wk 2 |  |  |  |  | Wk 3 |  |  |  |  | Wk 4 |  |  |  |  | Wk 5 |  |  |  |  | Wk 6 |  |  |  |  | Wk 7 |  |  |  |  | Wk 8 |  |  |  |  | Wk 9 |  |  |  |  | Wk 10 |  |  |  |  | Wk 11 |  |  |  |  | Wk 12 |  |  |  |  | Wk 13 |  |  |  |  | Wk 14 |  |  |  |  | Wk 15 |  |  |  |  | Wk 16 |  |  |  |  | Wk 17 |  |  |  |  | Wk 18 |  |  |  |  | Wk 19 |  |  |  |  | Wk 20
STATUS | PRIORITY | PROJECT NAMES + TASK TITLES | TASK DESCRIPTION | TASK OWNER | START DATE | END DATE | # of Days | DELIVERABLE | % COMPLETE | FIXED COST | EST. HOURS | ACTUAL HOURS | [100 empty] | STATUS | PRIORITY | time axis 2025-03-31 to 2025-08-15
In Progress | HIGH | PROJECT 1 |  |  | 2025-03-31 | 2025-04-21 | 16 |  | 74.33% | 22530 | 306 | 298 | [100 empty] | Not Started | LOW | bar: 2025-03-31 to 2025-08-15
In Progress | MED | P1 Task 1 |  |  | 2025-03-31 | 2025-04-03 | 4 |  | 33% | 8500 | 32 | 36 | [100 empty] | In Progress | MED | bar: 2025-03-31 to 2025-04-03
On Hold | MED | P1 Task 2 |  |  | 2025-04-02 | 2025-04-18 | 13 |  | 100% | 2500 | 104 | 100 | [100 empty] | Complete | HIGH | bar: 2025-04-02 to 2025-04-18
Overdue | HIGH | P1 Task 3 |  |  | 2025-04-13 | 2025-04-18 | 5 |  | 90% | 3200 | 40 | 40 | [100 empty] | On Hold | bar: 2025-04-14 to 2025-04-18
Needs Review | LOW | P1 Task 4 |  |  | 2025-04-03 | 2025-04-12 | 7 |  | 33% | 750 | 50 | 56 | [100 empty] | Overdue | bar: 2025-04-03 to 2025-04-11
Complete | MED | P1 Task 5 |  |  | 2025-04-09 | 2025-04-20 | 8 |  | 100% | 6380 | 64 | 56 | [100 empty] | Needs Review | bar: 2025-04-09 to 2025-04-18
Needs Update | HIGH | P1 Task 6 |  |  | 2025-04-18 | 2025-04-21 | 2 |  | 90% | 1200 | 16 | 10 | [100 empty] | Needs Update | bar: 2025-04-18 to 2025-04-21
In Progress | MED | PROJECT 2 |  |  | 2025-04-22 | 2025-06-21 | 44 |  | 21.67% | 16700 | 792 | 367 | bar: 2025-03-31 to 2025-08-15
Needs Update | LOW | P2 Task 1 |  |  | 2025-04-22 | 2025-06-21 | 44 |  | 70% | 2200 | 350 | 356 | bar: 2025-04-22 to 2025-06-20
In Progress | HIGH | P2 Task 2 |  |  | 2025-04-30 | 2025-05-02 | 3 |  | 60% | 14500 | 20 | 11 | bar: 2025-04-30 to 2025-05-02
Not Started | LOW | P2 Task 3 |  |  | 2025-05-05 | 2025-06-19 | 34 |  | 0% |  | 272 | bar: 2025-05-05 to 2025-06-19
Not Started | LOW | P2 Task 4 |  |  | 2025-05-06 | 2025-06-03 | 21 |  | 0% |  | 150 | bar: 2025-05-06 to 2025-06-03
|  | P2 Task 5 |  |  |  |  | 0 |  | 0%
|  | P2 Task 6 |  |  |  |  | 0 |  | 0%
Overdue | LOW | PROJECT 3 |  |  | 2025-04-14 | 2025-04-25 | 10 |  | 74.33% | 8350 | 112 | 99 | bar: 2025-03-31 to 2025-08-15
On Hold | MED | P3 Task 1 |  |  | 2025-04-14 | 2025-04-18 | 5 |  | 33% | 6500 | 40 | 36 | bar: 2025-04-14 to 2025-04-18
Complete | HIGH | P3 Task 2 |  |  | 2025-04-15 | 2025-04-16 | 2 |  | 100% |  | 16 | 12 | bar: 2025-04-15 to 2025-04-16
In Progress | LOW | P3 Task 3 |  |  | 2025-04-17 | 2025-04-17 | 1 |  | 90% |  | 5 | 5 | bar: 2025-04-17
Overdue | LOW | P3 Task 4 |  |  | 2025-04-21 | 2025-04-24 | 4 |  | 33% |  | 32 | 22 | bar: 2025-04-21 to 2025-04-24
Complete | LOW | P3 Task 5 |  |  | 2025-04-22 | 2025-04-23 | 2 |  | 100% | 1850 | 14 | 16 | bar: 2025-04-22 to 2025-04-23
Needs Review | MED | P3 Task 6 |  |  | 2025-04-25 | 2025-04-25 | 1 |  | 90% |  | 5 | 8 | bar: 2025-04-25
|  | PROJECT 4 |  |  | 0 | 0 | 0 |  | 0% | 0 | 0 | 0
|  | P4 Task 1 |  |  |  |  | 0 |  | 0%
|  | P4 Task 2 |  |  |  |  | 0 |  | 0%
|  | P4 Task 3 |  |  |  |  | 0 |  | 0%
|  | P4 Task 4 |  |  |  |  | 0 |  | 0%
|  | P4 Task 5 |  |  |  |  | 0 |  | 0%
|  | P4 Task 6 |  |  |  |  | 0 |  | 0%
|  | PROJECT 5 |  |  | 0 | 0 | 0 |  | 0% | 0 | 0 | 0
|  | P5 Task 1 |  |  |  |  | 0 |  | 0%
|  | P5 Task 2 |  |  |  |  | 0 |  | 0%
|  | P5 Task 3 |  |  |  |  | 0 |  | 0%
|  | P5 Task 4 |  |  |  |  | 0 |  | 0%
|  | P5 Task 5 |  |  |  |  | 0 |  | 0%
|  | P5 Task 6 |  |  |  |  | 0 |  | 0%
CLICK HERE TO CREATE IN SMARTSHEET | bar: 2025-03-31 to 2025-04-15

## BLANK - Multi-Project Gantt
MULTI-PROJECT GANTT CHART PLANNER
COMPANY NAME |  |  |  |  | START DATE
[5 empty] | 2025-03-31 |  |  | <-- Enter initial Start Date to populate Timeline dates.
|  | PROJECTS | [5 empty] | DELIVERABLES |  | COST / HOURS |  |  | Wk 1 |  |  |  |  | Wk 2 |  |  |  |  | Wk 3 |  |  |  |  | Wk 4 |  |  |  |  | Wk 5 |  |  |  |  | Wk 6 |  |  |  |  | Wk 7 |  |  |  |  | Wk 8 |  |  |  |  | Wk 9 |  |  |  |  | Wk 10 |  |  |  |  | Wk 11 |  |  |  |  | Wk 12 |  |  |  |  | Wk 13 |  |  |  |  | Wk 14 |  |  |  |  | Wk 15 |  |  |  |  | Wk 16 |  |  |  |  | Wk 17 |  |  |  |  | Wk 18 |  |  |  |  | Wk 19 |  |  |  |  | Wk 20
STATUS | PRIORITY | PROJECT NAMES + TASK TITLES | TASK DESCRIPTION | TASK OWNER | START DATE | END DATE | # of Days | DELIVERABLE | % COMPLETE | FIXED COST | EST. HOURS | ACTUAL HOURS | [100 empty] | STATUS | PRIORITY | time axis 2025-03-31 to 2025-08-15
|  | PROJECT 1 |  |  | 0 | 0 | 0 |  | 41.67% | 0 | 0 | 0 | [100 empty] | Not Started | LOW
|  | P1 Task 1 |  |  |  |  | 0 |  | 10% | [103 empty] | In Progress | MED
|  | P1 Task 2 |  |  |  |  | 0 |  | 20% | [103 empty] | Complete | HIGH
|  | P1 Task 3 |  |  |  |  | 0 |  | 30% | [103 empty] | On Hold
|  | P1 Task 4 |  |  |  |  | 0 |  | 40% | [103 empty] | Overdue
|  | P1 Task 5 |  |  |  |  | 0 |  | 50% | [103 empty] | Needs Review
|  | P1 Task 6 |  |  |  |  | 0 |  | 100% | [103 empty] | Needs Update
|  | PROJECT 2 |  |  | 0 | 0 | 0 |  | 0% | 0 | 0 | 0
|  | P2 Task 1 |  |  |  |  | 0 |  | 0%
|  | P2 Task 2 |  |  |  |  | 0 |  | 0%
|  | P2 Task 3 |  |  |  |  | 0 |  | 0%
|  | P2 Task 4 |  |  |  |  | 0 |  | 0%
|  | P2 Task 5 |  |  |  |  | 0 |  | 0%
|  | P2 Task 6 |  |  |  |  | 0 |  | 0%
|  | PROJECT 3 |  |  | 0 | 0 | 0 |  | 0% | 0 | 0 | 0
|  | P3 Task 1 |  |  |  |  | 0 |  | 0%
|  | P3 Task 2 |  |  |  |  | 0 |  | 0%
|  | P3 Task 3 |  |  |  |  | 0 |  | 0%
|  | P3 Task 4 |  |  |  |  | 0 |  | 0%
|  | P3 Task 5 |  |  |  |  | 0 |  | 0%
|  | P3 Task 6 |  |  |  |  | 0 |  | 0%
|  | PROJECT 4 |  |  | 0 | 0 | 0 |  | 0% | 0 | 0 | 0
|  | P4 Task 1 |  |  |  |  | 0 |  | 0%
|  | P4 Task 2 |  |  |  |  | 0 |  | 0%
|  | P4 Task 3 |  |  |  |  | 0 |  | 0%
|  | P4 Task 4 |  |  |  |  | 0 |  | 0%
|  | P4 Task 5 |  |  |  |  | 0 |  | 0%
|  | P4 Task 6 |  |  |  |  | 0 |  | 0%
|  | PROJECT 5 |  |  | 0 | 0 | 0 |  | 0% | 0 | 0 | 0
|  | P5 Task 1 |  |  |  |  | 0 |  | 0%
|  | P5 Task 2 |  |  |  |  | 0 |  | 0%
|  | P5 Task 3 |  |  |  |  | 0 |  | 0%
|  | P5 Task 4 |  |  |  |  | 0 |  | 0%
|  | P5 Task 5 |  |  |  |  | 0 |  | 0%
|  | P5 Task 6 |  |  |  |  | 0 |  | 0%

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.