## Project Charter Sample
PROJECT CHARTER SAMPLE
GENERAL PROJECT INFORMATION
PROJECT NAME |  |  | PROJECT MANAGER |  | PROJECT SPONSOR
User Experience Redesign |  |  | Michelle Fernet |  | Greg Jameson
EMAIL |  | PHONE | ORGANIZATIONAL UNIT
m.fernet@example.com |  | 000-000-0000
PROJECT OVERVIEW
PROBLEM OR ISSUE | Users report that the following steps are not intuitive: navigating to the cart and inputting credit card information.
PURPOSE OF PROJECT | We want to make the app more intuitive by using better UX design and by implementing photo integration for credit card information.
BUSINESS CASE | Making the app easier to use will result in increased sales and higher customer satisfaction.
GOALS/METRICS | We want the average customer review to increase from 3 stars to 4 stars, and we want monthly sales to increase by 15 percent.
EXPECTED DELIVERABLES | We expect to deliver a new app version that includes photo integration for capturing credit card information.
PROJECT SCOPE
WITHIN SCOPE | Within scope are the UI redesign of the cart and credit card information input pages, as well as the implementation of photo integration in order to capture credit card information.
OUTSIDE OF SCOPE | Outside of scope are the UI redesign of other app structures or anything outside the cart and credit card information pages.
TENTATIVE SCHEDULE
KEY MILESTONE |  |  | START |  | FINISH
Form Project Team / Preliminary Review / Scope |  |  | 01/03/20XX |  | 01/10/20XX
Finalize Project Plan / Charter / Kickoff |  |  | 01/11/20XX |  | 01/18/20XX
Perform Defining Phase |  |  | 01/19/20XX |  | 02/09/20XX
Perform Measurement Phase |  |  | 02/10/20XX |  | 03/10/20XX
Perform Analysis Phase |  |  | 03/10/20XX |  | 03/21/20XX
Perform Improvement Phase |  |  | 03/22/20XX |  | 04/05/20XX
Perform Control Phase |  |  | 04/06/20XX |  | 04/30/20XX
Deliver Project Summary Report and Close Out Project |  |  | 04/25/20XX |  | 05/05/20XX
RESOURCES
PROJECT TEAM | UX Research and Design Team
SUPPORT RESOURCES | Independent Research Contractor
SPECIAL NEEDS | None anticipated
COSTS
COST TYPE | VENDOR/LABOR NAMES |  | RATE | QTY | AMOUNT
Labor | UX Research and Design Team |  | 80 | 800 | 64000
Labor | Independent Research Contractor |  | 50 | 60 | 3000
Supplies | UX Test Gift Card Incentives |  | 25 | 50 | 1250
Supplies | Computers and Software |  | 3000 | 1 | 3000
|  |  | TOTAL COSTS |  | 71250
BENEFITS AND CUSTOMERS
PROCESS OWNER | Michelle Fernet
KEY STAKEHOLDERS | Greg Jameson, Michelle Fernet, Jasmine Porto, Hortencia Vida, Helena Creek
FINAL CUSTOMER | We want app shoppers and purchasers.
EXPECTED BENEFITS | We expect an increase in completed sales and an increase in the app's rating.
TYPE OF BENEFIT | BASIS OF ESTIMATE |  |  |  | ESTIMATED BENEFIT AMOUNT
Specific Cost Savings | IT chats about the inability to enter credit information will decrease. |  |  |  | 25000
Enhanced Revenues | Increases in completed sales and the app rating will increase annual sales. |  |  |  | 150000
|  |  | TOTAL BENEFIT |  | 175000
RISKS, CONSTRAINTS, AND ASSUMPTIONS
RISKS | Users may become frustrated by the new system's requirements: downloading a new update and reentering credit card information.
CONSTRAINTS | Because we need the UX team members for other projects (in addition to this one), they must complete the new app version for a 2/10 target rollout.
ASSUMPTIONS | Users will be willing to download a new update and reenter credit information if such actions lead to a better user experience overall.
PREPARED BY | TITLE |  |  |  | DATE
Michelle Fernet | Project Manager |  |  |  | 01/11/20XX
CLICK HERE TO CREATE IN SMARTSHEET
IMPORTANT REMINDER
The project sponsors must circulate and sign a narrative written charter. You can attach a completed version of this template to your narrative written charter in an effort to keep it short and concise.
Please make sure you meet with the project team and sponsors before completing this template. Having a discussion with these two parties will give you much of the information you need.

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.