## Agile Project Plan Example
IT AGILE PROJECT PLAN EXAMPLE TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
| Company ecommerce website rebuild | Alex B. | 2021-08-02 | 2021-11-02 |  | 20% |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Rework design |  | Alex B. |  | 2021-08-02 | 2021-09-04 | 33 | In Progress
| Determine design framework for all pages |  | Alex B. |  | 2021-08-02 | 2021-08-16 | 14 | Completed
| Design five new pages needed for site |  | Alex B. |  | 2021-08-17 | 2021-08-27 | 10 | In Progress
| Work on common design features needed for each page |  | Alex B. |  | 2021-08-27 | 2021-09-04 | 8 | Not Started
| Rework customer searching feature |  | Joanne C. |  | 2021-09-05 | 2021-09-27 | 22 | Not Started
| rebuild database of all products |  | Joanne C. |  | 2021-09-05 | 2021-09-18 | 13 | Not Started
| rebuild search module for website users |  | Tom M. |  | 2021-09-18 | 2021-09-27 | 9 | Not Started
| Rebuild ecommerce sales and checkout feature |  | Richard W. |  | 2021-09-28 | 2021-11-02 | 35 | Not Started
| Rebuild module that accepts customer payments |  | Richard W. |  | 2021-09-28 | 2021-10-05 | 7 | Not Started
| Rebuild architecture so customers can purchase products and checkout in three instead of four steps |  | Jennifer B. |  | 2021-10-05 | 2021-11-02 | 28 | Not Started
CLICK HERE TO CREATE IN SMARTSHEET

## Agile Project Plan - BLANK
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
Sprint 1
Feature 1
Feature 2
Feature 3
Sprint 2
Feature 4
Feature 5
Feature 6
Sprint 3
Feature 7
Feature 8
Feature 9

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.