## Strategic Project Planning
STRATEGIC PROJECT PLANNING TIMELINE TEMPLATE
PROJECT NAME |  | PREPARED BY
TASK | MONTH
| 1 |  | 2 | 3 | 4 | 5 | 6 | 7 | COLOR BLOCK EVENTS ACCORDING TO THEIR CALENDAR PLACEMENT
TIMELINE / APPROACH DEVELOPMENT
Garner consultant review of existing planning materials
Planning committee to discuss alternate approaches
Planning committee to finalize process and define desired outcomes
Summarize org history, accomplishments, and current status
Compile list of data required, and plan for gathering needed info
Develop list of stakeholders, and plan to solicit input
Present plan for board approval
Complete any necessary revisions; finalize plan
MISSION / VISION
Develop mission
Discuss organization values and goals
Gather stakeholder input regarding mission and vision
Polish statement
Approval / Finalize mission statement
INFORMATION GATHERING
Client surveys
Focus groups
Partner / Funder / Constituent interviews
Financial data prep
Comparative / Competitive studies
Environmental study
Current system and bylaw review
GOAL & PLAN FRAMEWORK DEVELOPMENT
Goal and objective brainstorming
Comprehensive review of all gathered data
Identify goal groupings
Prioritize goals
Ensure goals support mission statement and vision
Develop objective list
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Planning Timeline
STRATEGIC PROJECT PLANNING TIMELINE
PROJECT NAME |  | PREPARED BY
TASK | MONTH
| 1 |  | 2 | 3 | 4 | 5 | 6 | 7 | COLOR BLOCK EVENTS ACCORDING TO THEIR CALENDAR PLACEMENT
TIMELINE / APPROACH DEVELOPMENT
MISSION / VISION
INFORMATION GATHERING
GOAL & PLAN FRAMEWORK DEVELOPMENT

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.