## EX - Roles & Responsibilities
RACI ROLES AND RESPONSIBILITIES TEMPLATE
PROJECT TITLE
Launch New Website
DESCRIPTION
Update site with new look and feel
R Responsible A Accountable C Consulted I Informed
NAME | Diane Lockhart | Kalinda Sharma | Grace Florrick | Will Gardner
ROLE | CONTENT | DESIGNER | DEV | PM
PROJECT DELIVERABLE / ACTIVITY
PHASE 1: PROJECT PLANNING
Research | C | I | I | R
Interviews | A | C | C | I
Wireframe | R | C | I | A
PHASE 2: DEVELOPMENT
Provide Imagery | A | R | C | I
Systems Design | A | R | R | I
Systems Analysis and Requirements | A | A | R | C
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK Roles & Responsibilities
RACI ROLES AND RESPONSIBILITIES
PROJECT TITLE
DESCRIPTION
R Responsible A Accountable C Consulted I Informed | INSERT TEAM MEMBER PHOTO | PHOTO | PHOTO | PHOTO
NAME | [ TEAM MEMBER NAME ] | [ TEAM MEMBER NAME ] | [ TEAM MEMBER NAME ] | [ TEAM MEMBER NAME ]
ROLE | CONTENT | DESIGNER | DEV | PM
PROJECT DELIVERABLE / ACTIVITY
Initiate Phase Activities
Request Review by PMO | R
Submit Project Request |  | A
Research Solution |  |  | C
Develop Business Case |  |  |  | I
Plan Phase Activities
Create Project Charter
Create Schedule
Create Add'l Plans as Required
Execute Phase Activities
Build Deliverables
Create Status Report
Control Phase Activities
Perform Change Management
Close Phase Activities
Create Lessons Learned
Create Project Closure Report

## RACI Key - do not delete -
RACI KEY
– DO NOT DELETE –
RACI KEY
R | Responsible
A | Accountable
C | Consulted
I | Informed

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.