## EXAMPLE Scope of Work Template
SIMPLE SCOPE OF WORK TEMPLATE SAMPLE
PROJECT NAME | Electric Vehicle-Charging Station Installations
COMPANY NAME | Positive Charge
POINT OF CONTACT | Wendy Williams
PHONE | 765-876-9876
EMAIL | Wendy.Williams@postivecharge.com
COMPANY MAILING ADDRESS | 9016 NE 186th, Boswell, WA 98011
PROJECT LOCATION | (various) U.S., Mexico, Canada
AUTHOR | Jane Matthews
DATE
SCOPE OF WORK
What does the project entail? What are the delivery methods?
Installation of 1,125 EV charging stations at 116 locations across the US, Mexico and Canada to accommodate malls' and service stations' EV-charging needs. Full details of the scope of this work are included in the attached documents, but, broadly, this project will entail the following for 17 unique sites in 3 different countries, and will include: Site Analysis; Infrastructural Planning; Utility Assessment; Integration; Final Prep; and Installation.
PROJECT DELIVERABLES
Note the tangible products / services resulting from this project.
Installations of 1,125 fully functional and licensed EV charging stations at 116 locations across the US, Mexico and Canada - 1,000 EV charging station in S. California - 100 in Canada - 25 in Mexico (see attached spec for geo-specific locations).
EXCLUSIONS
Positive Charge is not responsible for third-party / client locations preparatory work (e.g., permits for digging, city region electricity-availability logistics, etc.).
However, Positive Charge project managers can provide clients with a checklist to ensure their locations are adequately prepared for the installation of our EV charging stations.
MILESTONES
DELIVERY DATE | TASK | GOODS REQUIRED | SERVICES REQUIRED
Form Project Team / Preliminary Review / Scope
Analysis Phase
Control Phase
Project Summary Report and Close Out
STAKEHOLDERS
ID NUMBER | NAME & TITLE | ROLE / RESPONSIBILITY
78979687 | Janine Remagio – Project Manager
8542342 | David Coen – Chief Engineer
5672334 | Rita Preze – CEO
98712376 | Donald Smythe – Field Engineer
ESTIMATED COST
EXPENSE | DESCRIPTION |  |  | COST
INTERNAL LABOR | Electro Charge Logistics |  |  | 68768
EXTERNAL LABOR | Level 1 EVS |  |  | 68768
MATERIALS | EVS Fast Chargers |  |  | 68768
SERVICES | Power Conversion System Vendor |  |  | 68768
OTHER | Third-Party Software |  |  | 68768
|  |  | TOTAL | 343840
PAYMENT TERMS & CONDITIONS
Next 30 upon project completion. 10% retainage fee.
APPROVAL & COMMENTS
PROJECT OWNER | Steph Arjuna
SIGNATURE
DATE
PROJECT MANAGER | Rita Stevens
SIGNATURE
DATE
COMMENTS
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK Scope of Work Template
SIMPLE SCOPE OF WORK TEMPLATE
PROJECT NAME
COMPANY NAME
POINT OF CONTACT
PHONE
EMAIL
COMPANY MAILING ADDRESS
PROJECT LOCATION
AUTHOR
DATE
SCOPE OF WORK
What does the project entail? What are the delivery methods?
PROJECT DELIVERABLES
Note the tangible products / services resulting from this project.
EXCLUSIONS
MILESTONES
DELIVERY DATE | TASK | GOODS REQUIRED | SERVICES REQUIRED
STAKEHOLDERS
ID NUMBER | NAME & TITLE | ROLE / RESPONSIBILITY
ESTIMATED COST
EXPENSE | DESCRIPTION |  |  | COST
0
0
0
0
0
|  |  | TOTAL | 0
PAYMENT TERMS & CONDITIONS
APPROVAL & COMMENTS
PROJECT OWNER
SIGNATURE
DATE
PROJECT MANAGER
SIGNATURE
DATE
COMMENTS

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.