## EX - Construction Project Plan
CONSTRUCTION PROJECT PLAN TEMPLATE
PROJECT TITLE |  |  | START | END
Sigma Facility |  |  | 2025-09-21 | 2026-06-01
PROJECT MANAGER |  |  | PROJECT DURATION IN DAYS
Tasha C. |  |  | 254
TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS
Planning | In Progress | Michael L. | 2025-09-21 | 2025-09-30 | 10
Demo Prep | Not Started | Jason S. | 2025-10-01 | 2025-10-06 | 6
Demolition | Complete | Ricky W. | 2025-10-06 | 2025-10-24 | 19
Excavation | On Hold | Molly S. | 2025-10-25 | 2025-10-29 | 5
Concrete | In Progress | Molly S. | 2025-11-01 | 2025-11-13 | 13
Pre backfill | Complete | Ricky W. | 2025-11-13 | 2025-11-15 | 3
Framing | In Progress |  | 2025-10-25 | 2025-12-05 | 42
Roof | Needs Review |  | 2025-11-19 | 2025-12-10 | 22
Plumbing | Needs Review |  | 2025-10-29 | 2025-12-09 | 42
Windows | On Hold |  | 2025-11-22 | 2025-12-15 | 24
HVAC | Not Started |  | 2025-11-29 | 2025-12-20 | 22
Electrical | Not Started |  | 2025-12-10 | 2025-12-22 | 13
A/V | In Progress |  | 2025-12-10 | 2025-12-15 | 6
House wrap | In Progress |  | 2025-12-27 | 2025-12-30 | 4
Insulation | On Hold |  | 2025-12-03 | 2025-12-21 | 19
Drywall | In Progress |  | 2026-01-03 | 2026-01-23 | 21
Exterior stone | In Progress |  | 2026-01-03 | 2026-01-17 | 15
Exterior case work | In Progress |  | 2026-01-04 | 2026-01-13 | 10
Laundry/furnace room flooring | In Progress |  | 2026-02-16 | 2026-03-11 | 24
Hardwoods | In Progress |  | 2026-01-19 | 2026-03-10 | 51
Tile | In Progress |  | 2026-02-03 | 2026-02-14 | 12
Cabinets | In Progress |  | 2026-01-18 | 2026-03-06 | 48
Plumbing -hang sinks | In Progress |  | 2026-02-16 | 2026-02-23 | 8
Interior doors | In Progress |  | 2026-02-25 | 2026-03-09 | 13
Millwork | In Progress |  | 2026-02-15 | 2026-02-17 | 3
Interior painting | In Progress |  | 2026-02-28 | 2026-04-14 | 46
Stone Counters | In Progress |  | 2026-03-21 | 2026-03-31 | 11
Schedule Buffer | In Progress |  | 2026-02-28 | 2026-03-10 | 11
Decks | In Progress |  | 2026-02-28 | 2026-03-18 | 19
Interior doors- hang & hardware | In Progress |  | 2026-05-03 | 2026-05-13 | 11
Appliances | In Progress |  | 2026-05-02 | 2026-05-03 | 2
Plumbing | In Progress |  | 2026-05-02 | 2026-05-05 | 4
Electrical | In Progress |  | 2026-05-03 | 2026-05-11 | 9
Bathroom Glass | In Progress |  | 2026-05-09 | 2026-05-13 | 5
Garage Door dress up | In Progress |  | 2026-05-13 | 2026-05-18 | 6
FINAL Inspections | In Progress |  | 2026-05-02 | 2026-05-02 | 1
Wrap up | Not Started |  | 2026-05-09 | 2026-06-05 | 28
House Cleaning | In Progress |  | 2026-05-29 | 2026-06-10 | 13
Complete | In Progress |  | 2026-06-10 | 2026-06-10 | 1
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Construction Plan
CONSTRUCTION PROJECT PLAN TEMPLATE
PROJECT TITLE |  |  | START | END
PROJECT MANAGER |  |  | PROJECT DURATION IN DAYS
TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS
Planning | In Progress
Demo Prep | Not Started
Demolition | Complete
Excavation | On Hold
Concrete | In Progress
Pre backfill | Complete
Framing | In Progress
Roof | Needs Review
Plumbing | Needs Review
Windows | On Hold
HVAC | Not Started
Electrical | Not Started
A/V | In Progress
House wrap | In Progress
Insulation | On Hold
Drywall | In Progress
Exterior stone | In Progress
Exterior case work | In Progress
Laundry/furnace room flooring | In Progress
Hardwoods | In Progress
Tile | In Progress
Cabinets | In Progress
Plumbing -hang sinks | In Progress
Interior doors | In Progress
Millwork | In Progress
Interior painting | In Progress
Stone Counters | In Progress
Schedule Buffer | In Progress
Decks | In Progress
Interior doors- hang & hardware | In Progress
Appliances | In Progress
Plumbing | In Progress
Electrical | In Progress
Bathroom Glass | In Progress
Garage Door dress up | In Progress
FINAL Inspections | In Progress
Wrap up | Not Started
House Cleaning | In Progress
Complete | In Progress
Double-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## Status Key - DO NOT DELETE
STATUS KEY - DO NOT DELETE
STATUS KEY
Not Started
In Progress
Complete
On Hold
Overdue
Needs Review

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.