## EXAMPLE Product Roadmap Gantt
PRODUCT ROADMAP GANTT CHART TEMPLATE EXAMPLE
NAME OF PRODUCT |  |  | PRODUCT MANAGER
Product ABC |  |  | Lee L.
COMPANY |  |  | START DATE
Valley View Inc. |  |  | 2025-09-02 |  |  | <-- Enter initial Start Date to populate Timeline dates.
[6 empty] | Wk 1 |  |  |  |  | Wk 2 |  |  |  |  | Wk 3 |  |  |  |  | Wk 4 |  |  |  |  | Wk 5 |  |  |  |  | Wk 6 |  |  |  |  | Wk 7
TASKS | TASK OWNER | STATUS | START | END | DAYS | 2025-09-01 | 2025-09-02 | 2025-09-03 | 2025-09-04 | 2025-09-05 | 2025-09-08 | 2025-09-09 | 2025-09-10 | 2025-09-11 | 2025-09-12 | 2025-09-15 | 2025-09-16 | 2025-09-17 | 2025-09-18 | 2025-09-19 | 2025-09-22 | 2025-09-23 | 2025-09-24 | 2025-09-25 | 2025-09-26 | 2025-09-29 | 2025-09-30 | 2025-10-01 | 2025-10-02 | 2025-10-03 | 2025-10-06 | 2025-10-07 | 2025-10-08 | 2025-10-09 | 2025-10-10 | 2025-10-13 | 2025-10-14 | 2025-10-15 | 2025-10-16 | 2025-10-17
Phase 1: Group Management controls & notifications | John K. | Complete | 2025-09-02 | 2025-09-05 | 4 | bar: 2025-09-01 to 2025-10-17
Pick list of locations |  | In Progress | 2025-09-02 | 2025-09-02 | 1 | bar: 2025-09-02
Improved console for IT manager |  | In Progress | 2025-09-02 | 2025-09-02 | 1 | bar: 2025-09-02
Product segment reports |  | Overdue | 2025-09-03 | 2025-09-03 | 1 | bar: 2025-09-03
|  | Needs Review | 2025-09-04 | 2025-09-04 | 1 | bar: 2025-09-04
|  | Needs Update | 2025-09-05 | 2025-09-05 | 1 | bar: 2025-09-05
Phase 2: Feature category |  | In Progress | 2025-09-05 | 2025-09-19 | 11 | bar: 2025-09-01 to 2025-10-17
Feature 1 |  | Complete | 2025-09-05 | 2025-09-05 | 1 | bar: 2025-09-05
Feature 2 |  | Complete | 2025-09-05 | 2025-09-05 | 1 | bar: 2025-09-05
Feature 3 |  | Canceled | 2025-09-08 | 2025-09-12 | 5 | bar: 2025-09-08 to 2025-09-12
|  | Complete | 2025-09-11 | 2025-09-15 | 3 | bar: 2025-09-11 to 2025-09-15
|  | Complete | 2025-09-15 | 2025-09-16 | 2 | bar: 2025-09-15 to 2025-09-16
|  | Complete | 2025-09-15 | 2025-09-16 | 2 | bar: 2025-09-15 to 2025-09-16
|  | Complete | 2025-09-17 | 2025-09-17 | 1 | bar: 2025-09-17
|  | Complete | 2025-09-18 | 2025-09-19 | 2 | bar: 2025-09-18 to 2025-09-19
Phase 3: Evaluate Potential Risks |  | Complete | 2025-09-15 | 2025-09-25 | 9 | bar: 2025-09-01 to 2025-10-17
Assess market size |  | Complete | 2025-09-15 | 2025-09-17 | 3 | bar: 2025-09-15 to 2025-09-17
Estimate competition |  | Complete | 2025-09-17 | 2025-09-18 | 2 | bar: 2025-09-17 to 2025-09-18
Conduct SWOT Analysis |  | Complete | 2025-09-18 | 2025-09-19 | 2 | bar: 2025-09-18 to 2025-09-19
Assess economic climate |  | Complete | 2025-09-19 | 2025-09-23 | 3 | bar: 2025-09-19 to 2025-09-23
Develop strategic plan |  | Complete | 2025-09-24 | 2025-09-25 | 2 | bar: 2025-09-24 to 2025-09-25
Phase 4: Attract Stakeholders |  | Complete | 2025-09-25 | 2025-10-07 | 9 | bar: 2025-09-01 to 2025-10-17
Establish management team |  | Complete | 2025-09-25 | 2025-09-29 | 3 | bar: 2025-09-25 to 2025-09-29
Seek strategic partnerships |  | Complete | 2025-09-30 | 2025-10-03 | 4 | bar: 2025-09-30 to 2025-10-03
Develop outreach plan |  | Complete | 2025-10-03 | 2025-10-07 | 3 | bar: 2025-10-03 to 2025-10-07
Phase 5: Development Stage |  | Complete | 2025-09-25 | 2025-10-07 | 9 | bar: 2025-09-01 to 2025-10-17
Create business plan outline |  | Complete | 2025-09-25 | 2025-09-29 | 3 | bar: 2025-09-25 to 2025-09-29
Fill in each section of business plan |  | Complete | 2025-09-30 | 2025-10-03 | 4 | bar: 2025-09-30 to 2025-10-03
Develop investor pitch deck |  | Complete | 2025-10-03 | 2025-10-07 | 3 | bar: 2025-10-03 to 2025-10-07
Phase 6: Establish Supporting Systems |  | Complete | 2025-10-07 | 2025-10-14 | 6 | bar: 2025-09-01 to 2025-10-17
Create bookkeeping systems |  | Complete | 2025-10-07 | 2025-10-08 | 2 | bar: 2025-10-07 to 2025-10-08
Create Manuals and Policies |  | Complete | 2025-10-08 | 2025-10-10 | 3 | bar: 2025-10-08 to 2025-10-10
Create company portal to store key documents |  | Complete | 2025-10-10 | 2025-10-14 | 3 | bar: 2025-10-10 to 2025-10-14
CLICK HERE TO CREATE IN SMARTSHEET | bar: 2025-09-01 to 2025-09-22

## BLANK Product Roadmap Gantt
PRODUCT ROADMAP GANTT CHART TEMPLATE
NAME OF PRODUCT |  |  | PRODUCT MANAGER
Name |  |  | Name
COMPANY |  |  | START DATE
Name |  |  | 2025-09-02 |  |  | <-- Enter initial Start Date to populate Timeline dates.
User to complete non-shaded fields only. | [5 empty] | Wk 1 |  |  |  |  | Wk 2 |  |  |  |  | Wk 3 |  |  |  |  | Wk 4 |  |  |  |  | Wk 5 |  |  |  |  | Wk 6 |  |  |  |  | Wk 7 |  |  |  |  | Wk 8 |  |  |  |  | Wk 9 |  |  |  |  | Wk 10 |  |  |  |  | Wk 11 |  |  |  |  | Wk 12 |  |  |  |  | Wk 13 |  |  |  |  | Wk 14 |  |  |  |  | Wk 15 |  |  |  |  | Wk 16 |  |  |  |  | Wk 17 |  |  |  |  | Wk 18 |  |  |  |  | Wk 19 |  |  |  |  | Wk 20
TASKS | TASK OWNER | STATUS | START DATE | END DATE | DAYS | time axis 2025-09-01 to 2026-01-16
|  |  | 0 | 0 | 0
0
0
0
0
0
|  |  | 0 | 0 | 0
0
0
0
0
0
0
0
0
|  |  | 0 | 0 | 0
0
0
0
0
0
|  |  | 0 | 0 | 0
0
0
0
|  |  | 0 | 0 | 0
0
0
0
|  |  | 0 | 0 | 0
0
0
0

## Status Keys - DO NOT DELETE
Drop Down Keys - DO NOT DELETE
STATUS
Not Started
In Progress
Complete
On Hold
Overdue
Needs Review
Needs Update
Canceled

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.