## EXAMPLE - Simple Software P
SIMPLE SOFTWARE PROJECT PLAN TEMPLATE
PROJECT NAME | PROJECT MANAGER | OVERALL PROGRESS | START DATE | END DATE | TOTAL DAYS | PROJECT DELIVERABLE
Product Release | Lexi W. | 20% | 2028-09-02 | 2028-10-10 | 38 | Deliverable
SCOPE STATEMENT
Scope statement
TASK NAME | ASSIGNED TO | PERCENT OF TASK COMPLETE | START | FINISH | DAYS | STATUS | NOTES
Sprint 1 | Lexi W. | 100% | 2022-09-02 | 2022-09-03 | 1 | COMPLETE
Feature 1 | Terry B | 22% | 2022-09-03 | 2022-09-07 | 4 | IN PROGRESS
Feature 2 | Artie B. | 30% | 2022-09-07 | 2022-09-12 | 5 | ON HOLD
Feature 3 | Jacob S. | 100% | 2022-09-09 | 2022-09-11 | 2 | COMPLETE
Sprint 2 | John K. | 20% | 2022-09-11 | 2022-09-15 | 4 | OVERDUE
Feature 4 | Dee W. | 0% | 2022-09-16 | 2022-09-17 | 1 | NOT STARTED
Feature 5 | Frank C. | 0% | 2022-09-17 | 2022-09-21 | 4 | NOT STARTED
Feature 6 | Shari W. | 60% | 2022-09-22 | 2022-09-24 | 2 | IN PROGRESS
Sprint 3 | Shari W. | 100% | 2022-09-23 | 2022-09-27 | 4 | COMPLETE
Feature 7 | Alex B. | 100% | 2022-09-25 | 2022-09-29 | 4 | COMPLETE
Feature 8 | Kennedy K. | 100% | 2022-09-24 | 2022-10-02 | 8 | COMPLETE
Feature 9 | Jacob S. | 100% | 2022-10-02 | 2022-10-05 | 3 | COMPLETE
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Simple Software Plan
SIMPLE SOFTWARE PROJECT PLAN TEMPLATE
PROJECT NAME | PROJECT MANAGER | OVERALL PROGRESS | START DATE | END DATE | TOTAL DAYS | PROJECT DELIVERABLE
Name | Name | 0% | MM/DD/YY | MM/DD/YY | #VALUE! | Deliverable
SCOPE STATEMENT
Scope statement
TASK NAME | ASSIGNED TO | PERCENT OF TASK COMPLETE | START | FINISH | DAYS | STATUS | NOTES
Sprint 1 |  | 0% | MM/DD | MM/DD | #VALUE! | COMPLETE
Feature 1 |  | 0% |  |  | 0 | IN PROGRESS
Feature 2 |  | 0% |  |  | 0 | ON HOLD
Feature 3 |  | 0% |  |  | 0 | COMPLETE
Sprint 2 |  | 0% |  |  | 0 | OVERDUE
Feature 4 |  | 0% |  |  | 0 | NOT STARTED
Feature 5 |  | 0% |  |  | 0 | NOT STARTED
Feature 6 |  | 0% |  |  | 0 | IN PROGRESS
Sprint 3 |  | 0% |  |  | 0 | COMPLETE
Feature 7 |  | 0% |  |  | 0 | COMPLETE
Feature 8 |  | 0% |  |  | 0 | COMPLETE
Feature 9 |  | 0% |  |  | 0 | COMPLETE

## Status Key - DO NOT DELETE
STATUS KEY - DO NOT DELETE
STATUS KEY
COMPLETE
IN PROGRESS
ON HOLD
OVERDUE
NOT STARTED

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.