## EXAMPLE Video Gantt Chart
VIDEO PRODUCTION GANTT CHART TEMPLATE EXAMPLE
PROJECT NAME | [6 empty] | START DATE
Video Project Alpha | [6 empty] | MM/DD/YY
PROJECT MANAGER | [6 empty] | END DATE
Micah E. | [6 empty] | MM/DD/YY
AT RISK | TASK | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS
| Choose a story | Complete | John K. | 2024-01-02 | 2024-01-08 | 6
| Determine length | In Progress | John K. | 2024-01-04 | 2024-01-11 | 7
| Write script | Not Started | Virginia W. | 2024-01-07 | 2024-01-11 | 4
| Create shooting script | Complete | Paul W. | 2024-01-10 | 2024-01-15 | 5
| Create script breakdown | Complete | Virginia W. | 2024-01-13 | 2024-01-20 | 7
| Create a storyboard | In Progress | Virginia W. | 2024-01-16 | 2024-01-29 | 13
| Determine the budget | On Hold | Malik M. | 2024-01-19 | 2024-02-01 | 13
| Scout and select locations | Complete | John K. | 2024-01-22 | 2024-02-09 | 18
| Get location permits and permissions | Complete |  | 2024-01-25 | 2024-02-05 | 11
| Determine equipment needs | Complete |  | 2024-01-28 | 2024-02-06 | 9
| Inventory existing equipment | Complete |  | 2024-01-31 | 2024-02-02 | 2
| Task 12 | Complete |  | 2024-02-04 | 2024-02-12 | 8
| Task 13 | Complete |  | 2024-02-06 | 2024-02-14 | 8
| Task 14 | Complete |  | 2024-02-09 | 2024-02-17 | 8
| Task 15 | Complete |  | 2024-02-18 | 2024-02-20 | 2
| Task 16 | Complete |  | 2024-02-15 | 2024-02-23 | 8
| Task 17 | Complete |  | 2024-02-18 | 2024-02-26 | 8
| Task 18 | Complete |  | 2024-02-21 | 2024-02-29 | 8
| Task 19 | Complete |  | 2024-02-24 | 2024-03-03 | 8
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK Video Gantt Chart
VIDEO PRODUCTION GANTT CHART TEMPLATE
PROJECT NAME | [6 empty] | START DATE
MM/DD/YY
PROJECT MANAGER | [6 empty] | END DATE
MM/DD/YY
AT RISK | TASK | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS
| Task 1 | Complete |  |  |  | 0
| Task 2 | In Progress |  |  |  | 0
| Task 3 | Not Started |  |  |  | 0
|  | Complete |  |  |  | 0
|  | Complete |  |  |  | 0
|  | In Progress |  |  |  | 0
|  | On Hold |  |  |  | 0
|  | Complete |  |  |  | 0
|  | Complete |  |  |  | 0
|  | Complete |  |  |  | 0
|  | Complete |  |  |  | 0
|  | Complete |  |  |  | 0
|  | Complete |  |  |  | 0
|  | Complete |  |  |  | 0
|  | Complete |  |  |  | 0
|  | Complete |  |  |  | 0
|  | Complete |  |  |  | 0
|  | Complete |  |  |  | 0
|  | Complete |  |  |  | 0
Double-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## Status Keys - DO NOT DELETE
STATUS KEYS - DO NOT DELETE
STATUS
Not Started
In Progress
Complete
On Hold

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.