## EXAMPLE - Agile Sprint Burndown
AGILE SPRINT BURNDOWN CHART TEMPLATE
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1 | 8
Task |  |  | Complete | 7 | 5 | 3 | 0 | 0 | 0 | 0
Task |  |  | In Progress | 3 | 1 | 1 | 5 | 0 | 1 | 0
Task |  |  | Not Started | 1 | 0.5 | 0 | 3 | 0 | 0 | 0
Task |  |  | Needs Review | 0.5 | 1 | 2 | 3 | 1 | 0 | 0
User Story #2 | 1
Task |  |  | Approved | 3 | 3 | 0.5 | 0.5 | 0 | 0 | 2
Task |  |  | Overdue | 3 | 5 | 5 | 1 | 1 | 1 | 0
Task |  |  | On Hold | 2 | 2 | 5 | 0 | 1 | 0 | 1
Task |  |  |  | 5 | 5 | 9 | 5 | 1 | 0 | 1
User Story #3 | 5
Task |  |  |  | 8 | 6 | 0 | 0 | 0 | 0 | 0
Task |  |  |  | 3 | 1 | 3 | 3 | 3 | 0 | 0
Task |  |  |  | 1.5 | 1 | 0.5 | 0.5 | 1 | 1 | 0
Task |  |  |  | 2 | 0.5 | 0 | 0 | 0 | 0 | 3
User Story #4 | 8
Task |  |  |  | 9 | 4 | 2 | 2 | 1 | 1 | 0
Task |  |  |  | 6 | 6 | 3 | 3 | 3 | 1 | 1
Task |  |  |  | 6 | 2 | 8 | 8 | 1 | 0 | 1
Task |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
User Story #5 | 3
Task |  |  |  | 2 | 1 | 1 | 1 | 0.5 | 1 | 1
Task |  |  |  | 6 | 6 | 6 | 0.5 | 3 | 9 | 0
Task |  |  |  | 9 | 9 | 9 | 4 | 3 | 3 | 3
Task |  |  |  | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 0 | 1
TOTAL |  |  |  | 78 | 60 | 59 | 41 | 20 | 18 | 14
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Agile Sprint Burndown
AGILE SPRINT BURNDOWN CHART TEMPLATE
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1
Task
Task
Task
Task
User Story #2
Task
Task
Task
Task
User Story #3
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
YES / NO | PRIORITY | STATUS
Yes | Low | Not Started
No | Medium | In Progress
| High | Complete
Needs Review
Approved
Overdue
On Hold

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.