## EXAMPLE - Risk Burndown Chart
RISK BURNDOWN CHART TEMPLATE
PROJECT NAME |  |  | DATE | STATUS | % COMPLETE
Pilot Program – Spring 20XX |  |  | 00/00/00 | ON TRACK | 88%
PROJECT TIMELINE
DASHBOARD DATA
WORKSTREAMS
DESCRIPTION | START DATE | END DATE | DURATION in days | OWNER | STATUS | PRIORITY | RISK | COMMENTS
Set Kick-Off Meeting | 2027-01-02 | 2027-01-08 | 7 |  | On Schedule | High | No Risk
Agree on Objectives | 2027-01-04 | 2027-01-11 | 8 |  | On Schedule | Medium | Low Risk
Determine Staffing | 2027-01-07 | 2027-01-11 | 5 |  | On Schedule | Low | Medium
Develop Messaging | 2027-01-10 | 2027-01-15 | 6 |  | On Schedule | Low | High
Finalize Budget | 2027-01-13 | 2027-01-20 | 8 |  | On Schedule | Low | Extreme
Email Outreach | 2027-01-16 | 2027-01-29 | 14 |  | Needs Attention | High | No Risk
Design Landing Page | 2027-01-19 | 2027-02-01 | 14 |  | Needs Attention | High | Low Risk
Targeted Blog Post | 2027-01-22 | 2027-02-09 | 19 |  | On Schedule | High | Medium
Video Production | 2027-01-25 | 2027-02-05 | 12 |  | Delayed | High | High
Ad Content | 2027-01-28 | 2027-02-06 | 10 |  | Delayed | High | Extreme
Social Media Promotion | 2027-01-31 | 2027-02-11 | 12 |  | On Schedule | Medium | No Risk
STATUS % |  |  |  | CAMPAIGN BUDGET
STATUS | COUNT | % |  | PROJECTED | 80000
On Schedule | 7 | 63.64% |  | USED | 50000
Needs Attention | 2 | 18.18% |  | REMAINING | 30000
Delayed | 2 | 18.18%
TOTAL | 11 | 100%
PRIORITY % |  |  |  | PENDING ITEMS
PRIORITY | COUNT | % |  | Decisions | 5
High | 6 | 54.55% |  | Actions | 2
Medium | 2 | 18.18% |  | Change Requests | 4
Low | 3 | 27.27%
TOTAL | 11 | 100%
RISK LEVEL %
RISK LEVEL | COUNT | %
No Risk | 3 | 27.27%
Low Risk | 2 | 18.18%
Medium | 2 | 18.18%
High | 2 | 18.18%
Extreme | 2 | 18.18%
TOTAL | 11 | 100%
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Risk Burndown Chart
RISK BURNDOWN CHART TEMPLATE
PROJECT NAME |  |  | DATE | STATUS | % COMPLETE
|  |  | 00/00/00 | ON TRACK | 0%
PROJECT TIMELINE
DASHBOARD DATA
WORKSTREAMS
DESCRIPTION | START DATE | END DATE | DURATION in days | OWNER | STATUS | PRIORITY | RISK | COMMENTS
Set Kick-Off Meeting |  |  | 0
Agree on Objectives |  |  | 0
Determine Staffing |  |  | 0
Develop Messaging |  |  | 0
Finalize Budget |  |  | 0
Email Outreach |  |  | 0
Design Landing Page |  |  | 0
Targeted Blog Post |  |  | 0
Video Production |  |  | 0
Ad Content |  |  | 0
Social Media Promotion |  |  | 0
STATUS % |  |  |  | CAMPAIGN BUDGET
STATUS | COUNT | % |  | PROJECTED | 0
On Schedule | 0 |  |  | USED | 0
Needs Attention | 0 |  |  | REMAINING | 0
Delayed | 0
TOTAL | 0 | 0%
PRIORITY % |  |  |  | PENDING ITEMS
PRIORITY | COUNT | % |  | Decisions | 0
High | 0 |  |  | Actions | 0
Medium | 0 |  |  | Change Requests | 0
Low | 0
TOTAL | 0 | 0%
RISK LEVEL %
RISK LEVEL | COUNT | %
No Risk | 0
Low Risk | 0
Medium | 0
High | 0
Extreme | 0
TOTAL | 0 | 0%
Right-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
STATUS | PRIORITY | RISK
On Schedule | High | No Risk
Needs Attention | Medium | Low Risk
Delayed | Low | Medium
High
Extreme

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.