## EXAMPLE - Campaign Roadmap
STRATEGIC MARKETING CAMPAIGN ROADMAP TEMPLATE
CAMPAIGN NAME |  |  | DATE | STATUS | % COMPLETE
Strategic Marketing Campaign – Spring 20XX |  |  | 00/00/00 | ON TRACK | 72%
CAMPAIGN ROADMAP
DASHBOARD DATA
WORKSTREAMS
DESCRIPTION | START DATE | END DATE | DURATION in days | OWNER | STATUS | PRIORITY | COMMENTS
Set Kick-Off Meeting | 2027-01-02 | 2027-01-08 | 7 |  | On Schedule | High
Agree on Objectives | 2027-01-04 | 2027-01-11 | 8 |  | On Schedule | Medium
Determine Staffing | 2027-01-07 | 2027-01-11 | 5 |  | On Schedule | Low
Develop Messaging | 2027-01-10 | 2027-01-15 | 6 |  | On Schedule | Low
Finalize Budget | 2027-01-13 | 2027-01-20 | 8 |  | On Schedule | Low
Email Outreach | 2027-01-16 | 2027-01-29 | 14 |  | Needs Attention | High
Design Landing Page | 2027-01-19 | 2027-02-01 | 14 |  | Needs Attention | High
Targeted Blog Post | 2027-01-22 | 2027-02-09 | 19 |  | On Schedule | High
Video Production | 2027-01-25 | 2027-02-05 | 12 |  | Delayed | High
Ad Content | 2027-01-28 | 2027-02-06 | 10 |  | Delayed | High
Social Media Promotion | 2027-01-31 | 2027-02-11 | 12 |  | On Schedule | Medium
STATUS % |  |  |  | CAMPAIGN BUDGET
STATUS | COUNT | % |  | PROJECTED | 80000
On Schedule | 7 | 63.64% |  | USED | 50000
Needs Attention | 2 | 18.18% |  | REMAINING | 30000
Delayed | 2 | 18.18%
TOTAL | 11 | 100%
PRIORITY % |  |  |  | PENDING ITEMS
PRIORITY | COUNT | % |  | Decisions | 5
High | 6 | 54.55% |  | Actions | 2
Medium | 2 | 18.18% |  | Change Requests | 4
Low | 3 | 27.27%
TOTAL | 11 | 100%
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Campaign Roadmap
STRATEGIC MARKETING CAMPAIGN ROADMAP TEMPLATE
CAMPAIGN NAME |  |  | DATE | STATUS | % COMPLETE
|  |  | 00/00/00 | ON TRACK | 100%
CAMPAIGN ROADMAP
DASHBOARD DATA
WORKSTREAMS
DESCRIPTION | START DATE | END DATE | DURATION in days | OWNER | STATUS | PRIORITY | COMMENTS
Set Kick-Off Meeting
Agree on Objectives
Determine Staffing
Develop Messaging
Finalize Budget
Email Outreach
Design Landing Page
Targeted Blog Post
Video Production
Ad Content
Social Media Promotion
STATUS % |  |  |  | CAMPAIGN BUDGET
STATUS | COUNT | % |  | PROJECTED | 0
On Schedule | 0 |  |  | USED | 0
Needs Attention | 0 |  |  | REMAINING | 0
Delayed | 0
TOTAL | 0 | 0%
PRIORITY % |  |  |  | PENDING ITEMS
PRIORITY | COUNT | % |  | Decisions | 0
High | 0 |  |  | Actions | 0
Medium | 0 |  |  | Change Requests | 0
Low | 0
TOTAL | 0 | 0%
Right-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
STATUS | PRIORITY
On Schedule | High
Needs Attention | Medium
Delayed | Low

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.