## EXAMPLE - Mutual Action Plan
EXAMPLE MUTUAL ACTION PLAN TEMPLATE WITH TIMELINE
PROJECT DETAILS
DUE DATE | MILESTONES | POSITION | OWNER | STATUS | NOTES
2026-03-03 | Initial Meeting | 1 | Owner 1 | Complete
2026-06-07 | Present Business Case | 3 | Owner 2 | Complete
2026-07-21 | Goals and Requirements Defined | 5 | Owner 3 | Complete
2026-08-01 | Confirm Success Criteria | 7 | Owner 4 | In Progress
2026-09-20 | Proof of Value Demo | 1 | Owner 5 | In Progress
2026-10-30 | Business Recommendation | 3 | Owner 6 | On Hold
2027-01-30 | Security and Legal Review | 5 | Owner 7 | On Hold
2027-02-10 | Contract Approval | 7 | Owner 8 | Not Started
2027-03-30 | Final Negotiations | 1 | Owner 9 | In Progress
2027-05-20 | Implementation | 3 | Owner 10 | Not Started
2027-10-31 | Success Review | 5 | Owner 11 | Not Started
CLICK HERE TO CREATE IN SMARTSHEET

## Status Key
STATUS KEY
Not Started
In Progress
Complete
On Hold

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk. This template is provided as a sample only. This template is in no way meant as legal or compliance advice. Users of the template must determine what information is necessary and needed to accomplish their objectives.