## EXAMPLE - Critical Path Diagram
CRITICAL PATH NETWORK DIAGRAM EXAMPLE
Use red arrows to illustrate the critical path.
CLICK HERE TO CREATE IN SMARTSHEET
ES
DUR
EF
TASK ID
LS
TF
LF
0
4
4
Clear Const Site
0
0
4
ES = Earliest Start
DUR = Duration
EF = Earliest Finish
LS = Latest Start
TF = Total Float
LF = Latest Finish
4
3
7
Lay foundation
4
0
7
7
12
19
Rough framing
7
0
19
19
3
22
Install windows, doors
19
0
22
22
4
26
Install drywall
22
0
26
19
5
24
Install electrical, plumbing
22
5
27
26
2
28
Interior Paint
27
1
29
24
2
26
Install fixtures
27
3
29
26
3
29
Install carpet, flooring
26
0
29
29
1
30
Final Inspection
29
0
30
24
2
26
Install faucets
27
3
29

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.