## Example - Simple Action Plan
SIMPLE ACTION PLAN TEMPLATE EXAMPLE
PROJECT NAME |  |  | PROJECT MANAGER |  |  | TODAY'S DATE
Project Beta |  |  | Bjorn Cavey |  |  | MM/DD/YY
ACTION PLAN
ACTION | RESPONSIBLE | PRIORITY | STATUS | START | END | NOTES
Goal #1: Select Venue |  | Medium | Complete
Identify venue options | Sally J. | High | Complete | 2022-09-30 | 2022-10-02
Visit venues | Sally J. | Medium | On Hold | 2022-10-05 | 2022-10-09 | Must send contracts by 10/10
Sign contract | Maria S. | Low | In Progress | 2022-10-12 | 2022-10-12
|  | Low | Complete
Goal #2: Secure Speakers |  | High | In Progress
Recruit speakers | Sally J. | Medium | In Progress | 2022-10-07 | 2022-10-12
Speaker bios | Sally J. | Medium | In Progress | 2022-10-12 | 2022-10-14
Create and send speaker packets | Maria S. | Low | Complete | 2022-10-13 | 2022-10-16 | Send to stakeholders
Confirm speakers | Sally J. | Medium | On Hold | 2022-10-17 | 2022-10-18
|  | Low | In Progress
Goal #3: Recruit Sponsors |  | Low | In Progress
Identify sponsors | John S. | Low | In Progress | 2022-10-13 | 2022-10-19
Write up sponsor agreement | Maria S. | Low | In Progress | 2022-10-15 | 2022-10-16
Send emails | John S. | Low | Not Started | 2022-10-19 | 2022-10-21
Make cold calls | John S. | Low | Not Started | 2022-10-21 | 2022-10-23 | From sales team
|  | Low | On Hold
Goal #4: Promote event |  | High | Complete
Create banners | Morgan K. | High | Complete | 2022-10-26 | 2022-10-28
Order swag | Morgan K. | High | Complete | 2022-10-28 | 2022-10-28 | Coffee mugs, totes, pencils
Create social media strategy | Corrine J. | High | Complete | 2022-10-13 | 2022-10-26
Make marketing materials | Karen Z. | High | Complete | 2022-10-26 | 2022-10-30
|  | High | Complete
CLICK HERE TO CREATE IN SMARTSHEET

## Blank - Simple Action Plan
SIMPLE ACTION PLAN TEMPLATE
PROJECT NAME |  |  | PROJECT MANAGER |  |  | TODAY'S DATE
Name |  |  | Name |  |  | MM/DD/YY
ACTION PLAN
ACTION | RESPONSIBLE | PRIORITY | STATUS | START | END | NOTES
Goal #1: |  | Low | Not Started | MM/DD | MM/DD
|  | Low | Not Started
|  | Low | Not Started
|  | Low | Not Started
|  | Low | Not Started
Goal #2: |  | Low | Not Started
|  | Low | Not Started
|  | Low | Not Started
|  | Low | Not Started
|  | Low | Not Started
|  | Low | Not Started
Goal #3: |  | Low | Not Started
|  | Low | Not Started
|  | Low | Not Started
|  | Low | Not Started
|  | Low | Not Started
|  | Low | Not Started
Goal #4: |  | Low | Not Started
|  | Low | Not Started
|  | Low | Not Started
|  | Low | Not Started
|  | Low | Not Started
|  | Low | Not Started

## Dropdown Key - Do Not Delete
DROPDOWN KEY - DO NOT DELETE
PRIORITY KEY | STATUS KEY
Low | Complete
Medium | Not Started
High | In Progress
On Hold

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.