## BLANK - IT Project Gantt
IT PROJECT GANTT CHART WITH MILESTONES TEMPLATE
Insert tasks with start and end dates in the data table below; Duration in days and chart data will populate automatically. Enter Milestone descriptions in the icons above the chart, and move to corresponding date locations. Delete unused rows.
PROJECT TITLE
–
TASK NAME | START DATE | END DATE | DURATION in days
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
CLICK HERE TO CREATE IN SMARTSHEET
MILESTONE 1
Description
MILESTONE 2
Description
MILESTONE 3
Description
MILESTONE 4
Description
MILESTONE 5
Description
Right click Horizontal (Value) Axis to format Bound Minimum and Maximum settings under Axis Options.

## EXAMPLE - IT Project Gantt
IT PROJECT GANTT CHART WITH MILESTONES TEMPLATE – EXAMPLE
PROJECT TITLE
Gaming App
TASK NAME | START DATE | END DATE | DURATION in days
Planning | 2030-01-16 | 2030-01-21 | 6
Wireframes | 2030-01-22 | 2030-01-23 | 2
Image Sourcing | 2030-01-22 | 2030-01-28 | 7
Graphics | 2030-01-27 | 2030-01-29 | 3
Design | 2030-01-28 | 2030-02-04 | 8
Search Incorporation | 2030-02-05 | 2030-02-09 | 5
Standards | 2030-01-28 | 2030-02-05 | 9
Legal | 2030-02-04 | 2030-02-06 | 3
Testing | 2030-02-07 | 2030-02-10 | 4
Optimization | 2030-02-09 | 2030-02-12 | 4
Platform Adaptation | 2030-02-11 | 2030-02-14 | 4
App Development | 2030-02-15 | 2030-02-17 | 3
Marketing | 2030-01-28 | 2030-02-05 | 9
Rollout | 2030-02-04 | 2030-02-06 | 3
Documentation | 2030-02-07 | 2030-02-10 | 4
Quality Assurance | 2030-02-09 | 2030-02-12 | 4
Validation | 2030-02-11 | 2030-02-14 | 4
Client Approval | 2030-02-15 | 2030-02-17 | 3
User Acceptance Testing | 2030-02-11 | 2030-02-14 | 4
Deployment | 2030-02-15 | 2030-02-17 | 3
MILESTONE 1
All Requirements Gathered
MILESTONE 2
Design Approval
MILESTONE 3
Optimization
MILESTONE 4
User Testing
MILESTONE 5
Deployment

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.