## Compatibility Matrix
Gantt Chart, PERT, CPM Compatibility Matrix
Instructions:
1. Print out the matrix; then gather a set of highlighters or colored pens.
2. Highlight each "I Want to" item according to its importance: green for "must-have," yellow for "nice-to-have," and red for "not necessary."
3. Compare each method's column for green "yes" responses; then consider yellow "yes" responses to determine which method best aligns with your highlighted priorities.
I Want to... | CPM | PERT | Gantt | CPM + PERT
Analyze large and complex projects | Yes | Yes | No | Yes
Use the critical path to determine project duration | Yes | Yes | No | Yes
Focus on time, schedule, and resource allocation | Yes | No | Yes | Yes
Understand task acceleration techniques like crashing | Yes | No | No | Yes
Assess projects with variable and uncertain time frames | No | Yes | No | Yes
Accelerate project completion by identifying essential tasks | Yes | Yes | No | Yes
Adjust the schedule when unforeseen challenges arise | Yes | No | No | Yes
Simplify project management for small projects | No | No | Yes | No
Avoid complexity and extensive data collection | No | No | Yes | No
Obtain a quick and easy-to-understand visualization | No | No | Yes | No
Focus solely on task durations and not on task dependencies | No | No | Yes | No
CLICK HERE TO CREATE IN SMARTSHEET

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.