## EXAMPLE - Tactic Tracking Gantt
SIMPLE TACTIC TRACKING GANTT TEMPLATE
PROJECT TITLE
PROJECT MANAGER |  | COMPANY NAME |  |  |  |  | DATE
[8 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
ACTION | ACTION | AMOUNT | ACTION | START | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
ID | TITLE |  | OWNER | DATE | DATE | IN DAYS | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | GIVEAWAY PROMO
1.1 | Item One | 200 | Leon W | 2029-03-12 | 2029-03-15 | 4 | 100% | bar: WEEK 1 F to WEEK 2 F
1.2 | Item Two | 250 | Kylie R | 2029-03-15 | 2029-03-16 | 2 | 100% | bar: WEEK 2 W to WEEK 2 F
1.3 | Item Three | 200 | Pete S | 2029-03-15 | 2029-03-21 | 7 | 90% | bar: WEEK 2 W to WEEK 3 R
1.4 | Item Four | 100 | Steve L | 2029-03-16 | 2029-03-22 | 7 | 40% | bar: WEEK 2 W to WEEK 3 R
1.5 | Item Five | 50 | Allen W | 2029-03-17 | 2029-03-22 | 6 | 70% | bar: WEEK 2 W to WEEK 3 R
1.6 | Item Six | 25 | Malik M | 2029-03-18 | 2029-03-22 | 5 | 60% | bar: WEEK 2 W to WEEK 3 R
1.7 | Item Seven | 1 | Malik M | 2029-03-23 | 2029-03-23 | 1 | 50% | bar: WEEK 2 W to WEEK 2 F; WEEK 3 F
2 | SURVEYS ISSUED
2.1 | Survey One | 600 | Steve L | 2029-03-24 | 2029-03-28 | 5 | 5% | bar: WEEK 2 W to WEEK 2 F; WEEK 4 M to WEEK 4 F
2.2 | Survey Two | 450 | Allen W | 2029-03-29 | 2029-04-02 | 5 | 30% | bar: WEEK 2 W to WEEK 2 F
2.3 |  |  | Malik M |  |  |  | 0% | bar: WEEK 2 W to WEEK 2 F
2.4 |  |  | Malik M |  |  |  | 0% | bar: WEEK 2 W to WEEK 2 F
3
3.1 |  |  | Pete S |  |  |  | 0% | bar: WEEK 2 W to WEEK 2 F
3.2 |  |  | Leon W |  |  |  | 0% | bar: WEEK 2 W to WEEK 2 F
3.2.1 |  |  | Kylie R |  |  |  | 0% | bar: WEEK 2 W to WEEK 2 F
3.2.2 |  |  | Kylie R |  |  |  | 0% | bar: WEEK 2 W to WEEK 2 F
3.3 |  |  | Pete S |  |  |  | 0% | bar: WEEK 2 W to WEEK 2 F
3.3.1 |  |  | Malik M |  |  |  | 0% | bar: WEEK 2 W to WEEK 2 F
4
4.1 |  |  | Steve L |  |  |  | 0% | bar: WEEK 2 W to WEEK 2 F
4.2 |  |  | Allen W |  |  |  | 0% | bar: WEEK 2 W to WEEK 2 F
4.3 |  |  | Malik M |  |  |  | 0% | bar: WEEK 2 W to WEEK 2 F
4.4 |  |  | Malik M |  |  |  | 0% | bar: WEEK 2 W to WEEK 2 F
CLICK HERE TO CREATE IN SMARTSHEET | bar: WEEK 1 M to WEEK 9 T
MILESTONE 1
Description
MILESTONE 2
Description
MILESTONE 3
Description
MILESTONE 4
Description
MILESTONE 5
Description

## BLANK - Tactic Tracking Gantt
SIMPLE TACTIC TRACKING GANTT TEMPLATE
PROJECT TITLE
PROJECT MANAGER |  | COMPANY NAME |  |  |  |  | DATE
[8 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
ACTION | ACTION | AMOUNT | ACTION | START | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
ID | TITLE |  | OWNER | DATE | DATE | IN DAYS | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1
1.1 | [6 empty] | 100% | bar: WEEK 1 T; WEEK 4 T; WEEK 7 T; WEEK 10 T
1.2 | [6 empty] | 0%
1.3 | [6 empty] | 0%
1.4 | [6 empty] | 0%
1.5 | [6 empty] | 0%
1.6 | [6 empty] | 0%
1.7 | [6 empty] | 0%
2
2.1 | [6 empty] | 0%
2.2 | [6 empty] | 0%
2.3 | [6 empty] | 0%
2.4 | [6 empty] | 0%
2.5 | [6 empty] | 0%
2.6 | [6 empty] | 0%
2.7 | [6 empty] | 0%
2.8 | [6 empty] | 0%
3
3.1 | [6 empty] | 0%
3.2 | [6 empty] | 0%
3.3 | [6 empty] | 0%
3.4 | [6 empty] | 0%
3.5 | [6 empty] | 0%
3.6 | [6 empty] | 0%
4
4.1 | [6 empty] | 0%
4.2 | [6 empty] | 0%
4.3 | [6 empty] | 0%
4.4 | [6 empty] | 0%
4.5 | [6 empty] | 0%
4.6 | [6 empty] | 0%
4.7 | [6 empty] | 0%
MILESTONE 1
Description
MILESTONE 2
Description
MILESTONE 3
Description
MILESTONE 4
Description
MILESTONE 5
Description

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.