## EXAMPLE - Stakeholder Update
STAKEHOLDER UPDATE TEMPLATE with MATRIX
PROJECT NAME | [5 empty] | PROJECT MANAGER |  | DATE | VERSION
Project Alpha | [5 empty] | Andrew W. |  | 00/00/0000 | 0.0.0
NAME OR GROUP | ROLE | PREDISPOSITION Enter "1" in selected Commitment Level |  |  |  | ANTICIPATED INVOLVEMENT | ANTICIPATED ISSUES | MOTIVATION / DRIVERS | EXPECTATIONS OF EXCHANGE | MILESTONES | ACTIVITIES | RESPONSIBLE PARTY | COMMUNICATION CHANNEL | COMMUNICATION FREQUENCY
Sponsors, managers, users, etc. |  | Current commitment profile: resistant, ambivalent, neutral, supportive/committed |  |  |  | What level of involvement is expected? | Known or potential issues | Why is the stakeholder invested in the project's success? | What is the stakeholder's predicted input? | At what point in the change effort is this stakeholder's involvement required? | What activities directly involve or impact the stakeholder? | Team member(s) responsible | What mode(s) of communication will be employed to disseminate info? | How often / at what interval will communications be disseminated?
|  | – | 0 | + | + +
Barbara B. | Manager | 1
Don W. | Jr Manager |  | 1 |  |  |  | ANTICIPATED INVOLVEMENT
Carrie B. | Associate |  | 1
Dino P. | Sr VP | 1
1
1
1
PREDISPOSITION TOTALS |  | 2 | 2 | 2 | 1
|  | – | 0 | + | + +
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Stakeholder Update
STAKEHOLDER UPDATE TEMPLATE with MATRIX
PROJECT NAME | [5 empty] | PROJECT MANAGER |  | DATE | VERSION
NAME OR GROUP | ROLE | PREDISPOSITION Enter "1" in selected Commitment Level |  |  |  | ANTICIPATED INVOLVEMENT | ANTICIPATED ISSUES | MOTIVATION / DRIVERS | EXPECTATIONS OF EXCHANGE | MILESTONES | ACTIVITIES | RESPONSIBLE PARTY | COMMUNICATION CHANNEL | COMMUNICATION FREQUENCY
Sponsors, managers, users, etc. |  | Current commitment profile: resistant, ambivalent, neutral, supportive/committed |  |  |  | What level of involvement is expected? | Known or potential issues | Why is the stakeholder invested in the project's success? | What is the stakeholder's predicted input? | At what point in the change effort is this stakeholder's involvement required? | What activities directly involve or impact the stakeholder? | Team member(s) responsible | What mode(s) of communication will be employed to disseminate info? | How often / at what interval will communications be disseminated?
|  | – | 0 | + | + +
ANTICIPATED INVOLVEMENT
PREDISPOSITION TOTALS |  | 0 | 0 | 0 | 0
|  | – | 0 | + | + +

## Stakeholder Commitment Matrix
STAKEHOLDER COMMITMENT MATRIX
HIGH | 0 | + +
| COMMIT | LEVERAGE
| NEGATIVE SUPPORT / | POSITIVE SUPPORT /
| HIGH INFLUENCE | HIGH INFLUENCE
| NEGATIVE SUPPORT / | POSITIVE SUPPORT /
| INVEST | PLAN
| MODERATE INFLUENCE | MODERATE INFLUENCE
LOW
| NEGATIVE SUPPORT / | POSITIVE SUPPORT /
| LOW INFLUENCE | LOW INFLUENCE
| MARGINALIZE | MAINTAIN
| – | +
| NEGATIVE | POSITIVE
0
+ +
–
+
SUPPORT
INFLUENCE

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.