## BLANK – Agile Epic Req
Agile Epic Requirements Template
1. Epic Overview
EPIC NAME
EPIC OWNER |  | EPIC ID | CREATION DATE | LAST UPDATED
2. Epic Description
SUMMARY
DETAILS
GOALS
3. Business Case
VALUE PROPOSITION
SUCCESS CRITERIA
DEPENDENCIES
4. Scope and Boundaries
IN SCOPE
OUT OF SCOPE
5. Acceptance Criteria
CONDITIONS OF SATISFACTION
DEFINITION OF DONE (DoD)
6. User Stories and Tasks
USER STORIES
User Story ID | Story Name
User Story Description
Acceptance Criteria
User Story ID | Story Name
User Story Description
Acceptance Criteria
TASKS
Task ID | Task Name |  | Description
7. Timeline | CREATION DATE |  | CREATION DATE
MILESTONE |  |  | DATE OF MILESTONE
8. Stakeholders
9. Risks and Assumptions
RISKS | MITIGATION PLANS |  | ASSUMPTIONS
10. Resources
TEAM MEMBERS
NAME |  | TITLE
TOOLS AND TECHNOLOGY
11. Progress Tracking |  |  | STATUS
PROGRESS UPDATES
12. Comments and Notes
CLICK HERE TO CREATE IN SMARTSHEET

## EXAMPLE – Agile Epic Req
Agile Epic Requirements Template – Example
1. Epic Overview
EPIC NAME
Real-Time Charging Station Monitoring
EPIC OWNER |  | EPIC ID | CREATION DATE | LAST UPDATED
Alexandra Mattson |  | PC-EPIC-001 | 07/22/20XX | 07/22/20XX
2. Epic Description
SUMMARY
Implement a real-time monitoring system for EV-charging stations to provide instant status updates and alerts.
DETAILS
This epic involves developing a robust monitoring solution that integrates with all charging stations, enabling real-time data collection and analysis. The system will display station availability, charging status, and performance metrics on a centralized dashboard.
GOALS
– Enhance operational efficiency by providing up-to-date station information. – Improve user satisfaction with real-time availability updates. – Enable proactive maintenance by identifying potential issues early.
3. Business Case
VALUE PROPOSITION
The real-time monitoring system will increase the efficiency and reliability of our EV-charging network, leading to higher customer satisfaction and reduced downtime.
SUCCESS CRITERIA
– Achieve 95% accuracy in real-time status updates. – Reduce downtime by 20%. – Receive positive feedback from at least 80% of users in post-implementation surveys.
DEPENDENCIES
– Complete the API integration with charging stations. – Make real-time data available from all stations.
4. Scope and Boundaries
IN SCOPE
– Develop a real-time monitoring dashboard. – Integrate the new system with existing charging stations. – Set up an alert and notification system for station status changes.
OUT OF SCOPE
– Integrate the new system with charging stations that are not yet deployed. – Create any features unrelated to monitoring.
5. Acceptance Criteria
CONDITIONS OF SATISFACTION
– The dashboard must display real-time status updates with less than a five-second delay. – The system must send alerts for any significant status changes or issues.
DEFINITION OF DONE (DoD)
– Code is reviewed and approved. – All unit and integration tests are passed. – User documentation is updated. – Stakeholder approval is obtained.
6. User Stories and Tasks
USER STORIES
User Story ID | Story Name
PC-US-001 | View Charging Station Status
User Story Description
As a user, I want to view the current status of charging stations in real time so that I can find an available station quickly.
Acceptance Criteria
The dashboard must show the real-time status of each station.
User Story ID | Story Name
PC-US-002 | Receive Status Alerts
User Story Description
As a maintenance team member, I want to receive alerts when a station goes offline so that I can address issues promptly.
Acceptance Criteria
The system must send alerts within one minute of a status change.
TASKS
Task ID | Task Name |  | Description
PC-TASK-001 | Develop Real-Time API Integration |  | Create an API to collect real-time data from charging stations.
PC-TASK-002 | Build Monitoring Dashboard |  | Develop a user interface to display real-time data.
PC-TASK-003 | Implement Alert System |  | Create a system to send alerts based on predefined conditions.
PC-TASK-004 | Conduct User Testing |  | Perform testing with a select group of users to gather feedback and identify issues.
7. Timeline | CREATION DATE |  | CREATION DATE
| Thursday, August 1, 20XX |  | Monday, September 30, 20XX
MILESTONE |  |  | DATE OF MILESTONE
API Integration Complete |  |  | Thursday, August 15, 20XX
Dashboard Development Complete |  |  | Monday, September 2, 20XX
User Testing Complete |  |  | Friday, September 20, 20XX
Final Review and Sign-Off |  |  | Monday, September 30, 20XX
8. Stakeholders
– Project Manager: Everett Crosse – Product Owner: Brooklyn Jansen – Development Team Lead: Henry McNeal – UAT Lead: Romy Bailey
9. Risks and Assumptions
RISKS | MITIGATION PLANS |  | ASSUMPTIONS
Potential delays in data integration from charging stations may occur. | Hold regular status meetings to monitor progress and address issues promptly. |  | All charging stations are capable of providing real-time data.
Unforeseen technical challenges in real-time data processing may arise. | Allocate additional resources for data integration tasks. |  | Required APIs are available and functional.
10. Resources
TEAM MEMBERS
NAME |  | TITLE
Henry McNeal |  | Development Team Lead
Jason Desjardins |  | Backend Developer
Makara McLean |  | Frontend Developer
Sasha Petrov |  | QA Engineer
TOOLS AND TECHNOLOGY
– API Gateway – Real-Time Data Processing Framework – Web Dashboard Framework
11. Progress Tracking |  |  | STATUS
In Progress
PROGRESS UPDATES
API integration development started on August 1, 20XX.
Initial dashboard design completed on August 10, 20XX.
12. Comments and Notes
Any additional notes or comments related to the epic can be added here for reference.

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.