## Corporate Event Timeline
Corporate Event Timeline Template
Event |  | Venue | [7 empty] | Date
Key Contacts
Name: |  | Email: | [7 empty] | Phone:
Name: |  | Email: | [7 empty] | Phone:
Name: |  | Email: | [7 empty] | Phone:
|  |  | PHASE ONE |  |  | PHASE TWO |  |  | PHASE TWO | PHASE TWO |  |  | PHASE THREE |  |  | PHASE FOUR |  |  | PHASE FIVE
TASK | ADDITIONAL INFO | ASSIGNED TO | Wk1 1 | Wk1 2 | Wk 3 | Wk4 | Wk5 | Wk6 | Wk7 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Wk 13 | Wk 14 | Wk 15
Phase 1: Initial Planning and Research
Define Objectives
Set Budget
Identify Stakeholders
Research Venues
Create Preliminary Schedule
Phase 2: Detailed Planning and Approvals
Refine Event Plan
Allocate Budget
Get Corporate Approvals
Select Vendors
Conduct Risk Management
Phase 3: Organizing and Booking
Secure Venue
Book Vendors
Arrange Speakers/Presenters
Plan Logistics
Conduct Internal Communication
Phase 4: Promotion and Final Preparations
Hold Launch Meetings
Finalize Program
Confirm Details
Send Invitations
Conduct Training and Rehearsals
Phase 5: Execution and Follow-Up
Execute Event
Ensure On-Site Coordination
Conduct Post-Event Surveys
Conduct Feedback Analysis
Prepare Final Reports
Reconcile Budget
CLICK HERE TO CREATE IN SMARTSHEET
Event Date
Define objectives and set budget
Identify stakeholders and research venues
Create preliminary schedule
Refine event plan and allocate budget
Get coporate approvals
Select vendors and conduct risk management
Secure venue and book vendors
Arrange speakers and presenters
Plan logistics and internal communication
Hold launch meetings
Finalize program and confirm details
Send invitations
Conduct training and rehearsals
Execute event with on-site coordination
Conduct post-event surveys and analyze feedback
Prepare final reports and reconcile budget

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.