## Team Resource Plan
TEAM RESOURCE PLANNING TEMPLATE
NAME
[5 empty] | Chantelle C. | Claudia K. | Kelly K. | Kevin D. | Maura T. | Paul B. | Ryan H. | Steve C. | KellyK. | Total Result
[5 empty] | 14 | 6 | 12 | 3 | 9 | 4 | 2 | 8 | 2 | 60
TASK | NAME | START DATE | END DATE | DURATION in days
Process Re-Engineering & Optimization Project | Steve C. | 2022-01-16 | 2022-01-21 | 5
Sub-Task 1 | Claudia K. | 2022-01-18 | 2022-01-21 | 3
Sub-Task 2 | Paul B. | 2022-01-22 | 2022-01-23 | 1
Sample Milestone - Zero Duration | Kevin D. | 2022-01-22 | 2022-01-23 | 1
Collaboration & Stakeholder Engagement Project | Kelly K. | 2022-01-22 | 2022-01-28 | 6
Sub-Task 1 | Ryan H. | 2022-01-27 | 2022-01-29 | 2
Sub-Task 2 | Maura T. | 2022-01-28 | 2022-02-04 | 7
Sub-Task 3 - Set Multiple Levels | Chantelle C. | 2022-02-05 | 2022-02-09 | 4
Sub-Sub-Task 1 | Chantelle C. | 2022-01-28 | 2022-02-05 | 8
Sub-Sub-Task 2 | Chantelle C. | 2022-02-04 | 2022-02-06 | 2
Process Architecture Project | Steve C. | 2022-02-07 | 2022-02-10 | 3
Sub-Task 1 | Claudia K. | 2022-02-09 | 2022-02-12 | 3
Sub-Task 2 | Paul B. | 2022-02-11 | 2022-02-14 | 3
Sample Milestone - Zero Duration | Kevin D. | 2022-02-15 | 2022-02-17 | 2
Customer Experience Project | Kelly K. | 2022-02-15 | 2022-02-17 | 2
Sub-Task 1 | Kelly K. | 2022-02-15 | 2022-02-17 | 2
Sub-Task 2 | KellyK. | 2022-02-15 | 2022-02-17 | 2
Sub-Task 3 - Set Multiple Levels | Kelly K. | 2022-02-15 | 2022-02-17 | 2
Sub-Sub-Task 1 | Maura T. | 2022-02-15 | 2022-02-17 | 2
CLICK HERE TO CREATE IN SMARTSHEET

## Team Resource Plan - BLANK
TEAM RESOURCE PLANNING TEMPLATE
NAME
[5 empty] | (empty) | Total Result
[5 empty] | 0 | 0
TASK | NAME | START DATE | END DATE | DURATION in days
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
TO RESET PIVOT TABLE DATA, after table has been updated, select "Refresh All" Under the Refresh menu on the "PivotTable Analyze" tab.
Chart will populate automatically.

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.